| SENATE SCRUTINY REPORT – SALIX DIRECT – CONTACT CENTRE ACTION PLAN: |  |  |  |  |  |  |  |  |  | Period covered (from / to): |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | June 2009 to September 2010 |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 1.Develop a training programme of ongoing training that Salix Homes | S | 01/06/09 | 30/06/09 | Sam Tindale//Jackie Rowlands | Skills and Knowledgeable staff | Number of CSR that have been through Salix Academy and NVQ training | N/A | N/A | Learning and Diversity Committee |  |
| 2.Develop and Agree a Customer Charter for Salix Homes that includes Salix Direct | S | 11/06/09 | 31/07/09 | Margaret Graham | Customers have clear standards of customer care which they can expect when interacting with staff at the contact centre and in person | Service standards One to one s – 360 degree feedback on competencies | N/A | N/A | Senate Customer Access and Involvement Panel Learning and Diversity Committee |  |
| 3.Customer to be involved in developing the SLA with Contact Centre. Include penalty clauses for failure to reach PI’s | S | 01/07/09 | 31/07/09 | Alison Hill/John Tanner | Customers will know what service to expect from the contact centre and be able to monitor their performance | Contact centre PI’s such as Customer Satisfaction Time to answer a call etc | N/A | N/A | Performance Committee Senate and SSP’s |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 4. Ensure learning from complaints is used to improve service delivery and publicised | S | 11/06/09 | 15/07/09 | William McKay | Improved Service Delivery | Reduce number of complaints | N/A | N/A | Performance Committee CI&A SSP |  |
| 5. Review how calls are categorised and referred to inbox | S | 01/06/09 | 31/07/09 | Sam Tindale | Increase number of calls answered at first point of contact | Increased Customer Satisfaction Reduction in number of calls being referred | N/A | N/A | CI&A SSP |  |
| 6.Publish performance data and advertised customers are involved in monitoring | S | 01/01/09 | 31/03/10 | Sam Tindale | Customers informed of performance across all service areas | N/A | N/A | N/A | Limelight Website |  |
| 7.Salix Direct to actively engage with the ‘mpathy’ housemark benchmarking | S | 26/05/09 | 30/06/09 | Michelle Gilmore | Services that are economic, efficient and effective. | Benchmarking against other public sector organisations | N/A | N/A | Performance Committee Senate and SSP’s |  |
| 8.Increase the added value service for customers by targeting customers | S | 01/07/09 | 31/03/10 | Contact Centre-Jackie Rowlands/Sam Tindale | Increase access to service | Increase the number of ‘added value’ services provide by ‘x’ % | N/A | N/A | CI&A SSP |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 9. Market Test the Contact Centre | S | 01/03/10 | 30/06/10 | Alison Hill/Margaret Graham | Ensures value for money in service delivery | N/A | N/A | N/A | Learning & Diversity Committee Senate/SSP’s |  |
| 10. Explore rent arrears with 6 weeks or more being diverted to Income Management Team | S | 08/06/09 | 30/06/09 | Sharon Simmonds | Customer receive a better service from appropriately skilled staff | Reduce avoidable contact Link to Income Management PI | 54 & 11 | N/A | Performance Committee |  |
| 11. Ensure that all letters to customers in arrears or high level ASB case have direct telephone numbers of the officers | S | 01/06/09 | 30/06/09 | Sharon Simmonds/ Warren Carlon | Personalise service to customers in most need | Mystery shop letters to customers | 11 | N/A | SSP’s |  |
| 12. Explore opportunity to refer nuisance calls directly to Safer Team | S | 01/07/09 | 31/07/09 | Warren Carlon | Improved Service Delivery | Reduce avoidable contact Increase the number of calls resolved at first point of contact | 11 | N/A | Performance Committee |  |
| 13. Explore the opportunity to provide a separate out of hours service for ASB | S | 01/07/09 | 31/07/09 | Warren Carlon/Margaret Graham | Improved Service Delivery | Increase Customer Satisfaction Reduce avoidable contact | N/A | N/A | Status Survey Performance Committee REACT |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 14. Explore the opportunity for all gas calls to be handle by Apollo | S | 01/04/10 | 30/06/10 | Matt Roberts/ Stephen Moore | Improved Service Delivery | Increase Customer Satisfaction Reduce avoidable contact | 11 | N/A | Performance Committee SSP |  |
| 15.Develop and introduce a repairs diagnostic tool kit (include training on) | S | 01/05/10 | 31/08/10 | Matt Roberts | Improved Service Delivery | Reduce avoidable contact Increase the number of calls resolved at first point of contact | 11 | N/A | Neighbourhoods Committee Performance Committee SSP |  |