| SENATE SCRUTINY REPORT – REPAIRS APPOINTMENTS ACTION PLAN: |  |  |  |  |  |  |  |  |  | Period covered (from / to): |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | September 2010 to March 31/03/11 |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 1. Include a clause in procurement templates to ensure contractors will interface with Northgate, the Integrated Housing Management System. | S | 01/08/10 | 30/09/10 | Matt Roberts | Customers will receive a consistent service | Number of procurement exercises that include clause Number of contractors appointed that interface with Northgate | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 2. Include a penalty clause in procurement templates for failure to attend appointments and contribute to the additional cost of avoidable contact | S | 01/08/10 | 30/09/10 | Matt Roberts | Customers will be able to rely on the appointment time | Number of appointments failed Amount of contribution paid | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 3. Develop a criterion that assists staff to offer an appropriate appointment. |  | 01/08/10 | 31/10/10 | Paul Lister/ Angela Houghton | Customers will receive a consistent service and receive an appropriate appointment | Number of hits on scripts % of appointments made and kept | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 4. Develop a script for managing customer expectation |  | 01/08/10 | 31/10/10 | Paul Lister/ Angela Houghton | Customers will receive a consistent service and receive an appropriate appointment | Number of hits on scripts 5% reduction in avoidable contact | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 5. Explore alternative opportunities and methods for gathering customer satisfaction | S | 01/09/10 | 31/12/10 | Paul Lister | Customers will be able to record their satisfaction in a variety of methods | N/A | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 6.Implement alternative methods for gathering customer satisfaction | S | 01/01/11 | 31/03/11 | Paul Lister | Customers will be able to record their satisfaction in a variety of methods | Increased Customer Satisfaction | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 7. Determine what ‘right first time’ means and explore the opportunity to identify repairs that require more than one appointment and offer adequate appointments. | S | 01/09/10 | 31/03/11 | Paul Lister | Customers will be aware of the requirements of the repair and their expectations are managed | Increased customer satisfaction | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 8. Develop a policy and procedure for penalising customers who fail to keep their appointments. | S | 01/09/10 | 31/03/11 | Paul Lister | Customers will be aware of their responsibility to be available for contractors | Reduce the number of failed appointments Increase the number of repairs resolved at first point of contact. | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 9. Develop protocol for use of repairs diagnostic tool kit to ensure the correct job is raised and the necessary appointment(s) are offered | S | 01/09/10 | 31/12/10 | Paul Lister | Ensures repairs are completed at first visit | Reduce number of repairs being wrongly diagnosed Reduce number of jobs ordered on the wrong priority | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 10. A new leaflet should be introduced to the customer handbook which states exactly what will happen on an appointment made for a gas service check. | S | 01/09/10 | 31/12/10 | Paul Lister | Customer are aware what should happen during a gas service | Increase access for gas servicing | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 11. Develop a label system which can be signed and dated then placed on the boiler to show when test was carried out | S | 01/09/10 | 31/12/10 | Paul Lister | Customer are aware when gas service should take place | Increase access for gas servicing | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 12. Arrange access to the emerging day diary for Salix Direct and Customer Services Officers with immediate effect. | S | 01/09/10 | 30/09/10 | Paul Lister | Customer expectation will be more effectively managed | Reduce avoidable contact Increase the number of calls resolved at first point of contact | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 13. Develop a process to monitor the effectiveness of appointment rescheduling if repairs cannot be completed at the first point of contact for both Jackson Lloyd and Liberty. | S | 01/09/10 | 31/12/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction Reduce avoidable contact | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 14. Develop a process to routinely check van stock. | S | 01/09/10 | 31/12/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction Reduce avoidable contact | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 15. Explore options for operatives to have fobs for low rise with specific regard to emphasising the responsibility for security on the blocks. | S | 01/09/10 | 31/12/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction Reduce avoidable contact Increase number of appointments kept | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 16. Develop a protocol for operatives undertaking multi repairs in high rise blocks to contact their next customer via the intercom system | S | 01/09/10 | 31/12/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction Reduce avoidable contact Increase number of appointments kept | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 17. Review information made available to operatives to ensure customer needs are met through effective use of profile information. | S | 01/09/10 | 31/12/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 18. Adopt Disability Protocol when signed off by the Disability Focus Group | S | 01/09/10 | 30/09/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 19. All operatives to be trained and reminded of the availability of language line | S | 01/09/10 | 30/09/10 | Paul Lister | Improved Service Delivery | Increase Customer Satisfaction | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 20. Salix Homes to review if language line is the most appropriate translation service | S | 01/09/10 | 31/03/11 | Daryl Stonebank | Customers receive the best possible translation service | Increase customer satisfaction Reduce avoidable contact | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |
| 21. Deliver a regular programme of training for operatives on the Salix Way and Your Customer Your responsibility |  | 01/09/10 | 31/03/11 | Ava Phillipps | Customers receive the best possible translation service | Increase customer satisfaction Reduce avoidable contact | N/A | N/A | Learning and Diversity Committee Investment and Maintenance SSP Senate |  |