## Action Plan
|  | This Action Plan refers to Property Summit, Rising Stars, The Big One, No Access Policy, and Focus. Please refer to the supporting document for further explanation of these references. | Key
|  |  | Green | Agreed Actions
|  |  | Blue | Disputed
|  |  | Green | Stephen Questel Responsible Staff
|  |  | Light Blue | Bill Bendle Responsible Staff
|  |  | Red | Barbara McPhearson Responsible Staff
|  |  | Blue | Andy Pearson Reponsible Staff
|  |  | Yellow | Stuart Faulkner Responsible Staff
|  |  | Orange | Emma Richman Responsible Staff
|  |  | Pink | Lauretta Rothery Responsible Staff
|  |  | RED | This represents recommendations that are effected by The Big One.
|  |  | WHITE | This represents recommendations that are effected by the No Access Strategy.
Strategic Theme | Ref | Action | Target | How to Address | Owner | Status / Timescale | Management Response | Audit Findings
Right First Time | 1 | Improve hub diagnosis of Repairs |  | Use 3D Technology to give hub a simulated view of all Trust Property Types. |  |  | This is something which is not part of the proposed Big One but the principle is good and will be picked up through the Property Summit meetings held quarterly.
RFT at Upper Quartile
| 2 |  |  | Shadowing of Technical Surveyors of all hub staff built into Rising Stars Objectives. | Andrew Pearson | 2013-09-01 | This will be part of the Job Description of the Technical Surveyor - by setting as an Objective within Rising Stars | Rising Stars being replaced in 2015/16. This objective will contiune and form part of the new JD for Tech Surveyors
| 3 |  |  | Repairs Operatives to spend one half day per year with hub staff , this is to be built into Rising Stars Objectives. | Andrew Pearson | 2013-09-01 | This will be part of the Job Description of the Operative - by setting as an Objective within Rising Stars
| 4 |  |  | Trouble Shooter Bible to be Produced. | Andrew Pearson | 2013-12-01 | Pictorial Booklet to be produced to assist Hub Staff , a copy to be provided to QIP for Comment.
| 5 |  |  | Jobs which require more than one appointment should be arranged at the outset. | Andrew Pearson | 2013-09-01 | AP to work with the Hub manager to implement this as mandatory for all Hub Staff, It will be part of the new script for The BICB.
| 6 |  |  | More Detailed Scripting. | Peter Lightbown | 2014-04-01 | AP to work with the Hub Manager to look at this prior to the implmentation of The BICB.
| 7 |  | Reduce Pre inspections by 10%. | Hub staff should be able to bypass the system and not raise pre inspections when they are able to raise the job straight away. | Peter Lightbown | 2014-04-01 | AP to work with the Hub Manager to implement this as Mandatory for all Hub Staff although the BICB will help montior this.
| 8 | More accurate diagnosis. |  | Technical Officers to telephone tenants when able to rather than visit. | Andrew Pearson | 2013-10-01 | This to be highlighted and monitored through Systems , at 1 to 1's and in Technical Team Meetings. | Confimed that approx 10% of all pre inspections are diagnosted by the inspector over the phone reducing site visits.
Reduce Pre Inspections.
| 9 | Increase Productivity. |  | Develop a process to monitor the effectiveness of appointment reschedule if repairs cannot be completed at the first point of contact. | Andrew Pearson | 2014-04-01 | This is to Process Mapped as part of the Big One as when the new system is implemented we can monitor and report on this.
Increase Productivity.
| 10 |  |  | Ensure all Contractors understand RFT and implications - Issue a letter to all followed by a training session for them. | Andrew Pearson | 2014-10-01 | There is only a small number of Sub Contractors and I propose holding a half day session when we can discuss Right First Time, Health and Safety and Method Statements. The new system will allow sub contracor performance to be recorded and monitored.
| 11 |  |  | Encourage more repairs operatives to become Dual Trade. | Andrew Pearson | 2014-04-01 | We can look at Budgeting for this 14/15. But we are unable to look at enhanced incentives the more qualifications they have. We work towards Rising Stars which does not offer Reward Related Pay, However this may change as the Business becomes more commercial | Continually Increasing Dual role staff through regular development programmes, we currently have 5 staff enrolling on various dual role courses in Sept 2015 . We are training staff in areas of high demand such as plastering.
| 12 |  |  | Look at Productivity and understand and reduce unproductive time when possible. | Andrew Pearson | 2014-04-01 | A recent Value For Money report on Productivity in Repairs , has recommendations that cover these points. The recommendations are currently being finalised and will be shared with the QIP once agreed and finalised. | We are in the final stages of introducing a balanaced score card to report on each individual operatives performance. This will give us forensic knowledge on all unproductive time to enable plans to be drawn up to address the issue.
| 13 |  |  | Within reason allow operatives to carry out additional repairs Identified at the same property and where possible allow them to inspect and carry out jobs to reduce waiting time. | Andrew Pearson | 2013-09-01 | This is to be encouraged through Systems, 1 to 1's and Team Meetings and when the new system is implemented in January we will be able to report on this.
| 14 |  |  | Ensure all technical officers always supply details of measurements , components and materials. | Andrew Pearson | 2013-09-01 | This is something that will be reinforced at 1 to 1's and Team meetings. There is to be a Technical Officer review in Q3 13/14 and we can ensure this is something that is investigated as part of the review. | Confirmation all Tech Inspectors are now supplying quality data including measurements on all jobs as per QIP recommendation.
| 15 |  |  | Separate workforce for tenant repairs and Handy fix and Adaptations. |  | 2015-01-01 | We have introduced flexible working to help the service respond with increased productivity. Day to Day, Handyfix and Adaptations are all set up as separate contracts, wioth dedicated staff that can be reported on seperately.
| 16 |  |  | All issues to do with repairs should be recorded and passed to Managers to monitor emerging trends. | Andrew Pearson | 2014-04-01 | This will become an item on the agenda of the Repairs / Regeneration monthly meeting that will look at emerging trends. However the Big One will allow these to be recorded more effectively.
No Access | 17 |  |  | The Hub should always inform and offer tenants a choice of appointments, including Evening and Saturday slots that are convenient for them | Stuart Faulkner | 2014-04-01 | ER to discuss this with Kath Aspray to ensure all appointment options are offered . This can be reinforced through Systems, 1 to 1's and Team Meetings. Part of the No Access Strategy also.
| 18 |  |  | When the hub book a timeslot they need to stress how important it is for tenants to keep their appointment and if they find they aren't going to be in , they should always ring and let staff know. | Stuart Faulkner | 2014-04-01 | ER to discuss this with Kath Aspray to ensure that the hub do stress the importance of keeping appointments . This can be reinforced through systems, 1 to 1's and Team Meetings. Part of the No Access Strategy also.
| 19 |  |  | In extreme circumstances, where tenants continually fail to be in for repair appointments, penalties need to be introduced to try and reduce the high cost of "No Access". | Stuart Faulkner | 2015-08-01 | As part of the BICB project, go live in August 15, THT will record the missed appointments either by THT staff or the customer. This information will assist in forming decisions on penalities for no access.
| 20 |  |  | Routinely ask tenants for their contact details at the beginning of each call to the hub , to ensure that despite tenants frequently changing their mobile numbers and email addresses, they will be kept up-to-date before, as well as after data cleansing has been carried out. | Stuart Faulkner | 2014-04-01 | ER to discuss this with Kath Aspray to ensure these details are being requested. This can be reinforced through Systems, 1 to 1's and Team Meetings. Part of the No Access Strategy and Policy.
| 21 |  |  | A phone call to the tenant should always be made on the day of the appointment before arriving at their home and repair operatives should not arrive considerably earlier , without first contacting the tenant to ask if this is convenient. | Stuart Faulkner | 2014-04-01 | This has been a Management Instruction for Operatives since February 13. Voluntas asks the question "were you conacted prior to the opertaive attending?"However it wil be formalised through the No Access Strategy and Policy.
Reduce No Access.
| 22 | Save Money. | No Access Policy | Discontinue "Carding" where new appointments are arranged without the agreement of the tenant. If tenants fail to be at home for pre - arranged appointments, then repairs operatives should simply leave a card asking tenants to ring the hub and re arrange another appointment. ( Repairs operatives now push a leaflet through the tenant's letterbox, informing them of the costs of "No Access." | Stuart Faulkner | 2014-04-01 | This is something that needs to be addressed through Systems, 1 to 1's and Team Meetings. The New system will allow us to monitor this more effectively,. It will form part of a No Access Strategy and Policy.
Increase awareness of available appoitments
| 23 |  |  | Tenants who continually fail to keep appointments, without good reason must go to the back of the queue and wait the 15 working day response time gain. | Stuart Faulkner | 2014-04-01 | This will be consulted at a Q3 Property Cag and will form part of a New No Access Policy and Strategy that will come to the QIP in draft.
Update accurate details
| 24 |  |  | Introduce appointment slots for even minor jobs, especially where there is restricted access, due to locked outer doors leading to back gardens. | Stuart Faulkner | 2014-04-01 | This is something we can enourgage now through Systems, 1 to 1's and Team Meetings. However the new system will make this easier and will be captured as part of a No Access Strategy and Policy.
| 25 |  |  | The Hub should routinely ask tenants if they have an email address when they report a repair. This would enable staff to send out reminders about repair appointments by email as well as voicemail or text. | Stuart Faulkner | 2014-04-01 | ER to discuss this with Kath Aspray to see how we can formally implement this now, however the new system will enable this information to be recorded more effectively. Also will be part of a No Access strategy and policy.
The Big One | 26 |  |  | Profiling should include those tenants who may be hard of hearing, blind or cannot answer the door quickly due to poor mobility , so that repairs operatives are aware of this when they arrive. | Diane Thompson | 2014-02-01 | Limited Profiling / Data Cleansing is currently taking place. However, The new system will allow this information to be requested and recorded more effectively. | Very effective new system now in place, the system captures quality knowledge around our customers and presents this through the mobile solution to the operatives ipad
| 27 |  |  | Where tenants have been profiled and identified as vulnerable , they are offered the opportunity of using code words, which repair operatives use to identify themselves when calling to carry out a repair. ( These tenants would then know they were genuine employees of the Trust and not bogus callers. | Diane Thompson | 2014-02-01 | This will be designed into the new system and Repairs Opratives will be trained on this aspect. | where this is requested by customer ,we are using code words , but this is not something that is offered volunterily by the hub.
| 28 |  |  | The hub should be able to view the same information as planners, such as repair schedules so that when tenants ring to cancel, change appointments , these calls can be dealt with by them, without the need to pass enquiries on to planners. ( However only planners should have the ability to plot and change schedules in relation to repairs operatives. | Diane Thompson | 2014-02-01 | This is an integral part of how scheduling of appointments will be work in the new system. The Hub will be able to directly make the appointments and see exactly what the Planners see.
| 29 |  |  | Encourage Contractors to communicate more effectively with THT through the Contractor Portal. This would allow more effective monitoring of external contracts. External contracts are low in number and it was agreed that it would be unrealistic to ask external contractors to use the same systems as the Trust as so few orders actually go to external contracts now. | Diane Thompson | 2014-02-01 | This something we will discuss when we have the half day session with External Contractors, refered to in Point 10. Closing the Contractor loop is a priority for the service.
Effective Profiling
| 30 | Increased view for Hub |  | All repair operatives should be using First Touch software (or similar) so that replacements are automatically re-ordered as stock is taken off the van and used, saving time and improving efficiency. Any inaccuracies with stock ordering , such as duplication and incorrect spares being supplied need to be raised with stores supplier. Technicians should investigate whether the correct codes are being used and if repairs operatives have had adequate training on the system. | Diane Thompson | 2014-02-01 | The Material stores contract is currently being procured and has the same timeframe as the big one. This is an integral part of both projects.
PDA Resolution
| 31 | Contractor links | Part of Big One | If a pre-inspection is needed then the response time (15 working days) should be counted from the date of the repair is actually reported by the tenant, not from the date of the pre-inspection). Alternatively introduce a target time for pre-inspections, so that the response times for all routine repairs do not exceed more than twenty working days start to finish. ( Although it is acknowledged that with larger jobs , where Contractors may be needed, this won't always be possible.) | Diane Thompson | 2014-02-01 | This has ben captured within the Big One, the calculation will be from when it is reported and there is a target time of set for preinspections.
|  | Van Stock Control | Part of Benefit
| 32 | Pre Inspection included | Realisation Document | Where poor satisfaction levels are expressed by tenants and recorded as service failures, managers should carry out spot checks and record their findings. When tenants contact the Trust about any issues they have these should be recorded and passed to managers, so that they are aware of them and can monitor any problems that arise. | Diane Thompson | 2014-02-01 | Although this is something we have formalised in the new system. It is something that is done but ER needs to highlight in Manager Team Meetings. | All complaints and poor satisfaction survey information is captured and every dis satisfied customer is contacted to ensur ethe service learns from any issues raised. Current customer satisfaction levels for responsive repairs are 97% with a target set at 90%.
Satisfaction Recording
| 33 | Effective Online Reporting |  | Simplify online reporting of repairs by incorporating more visual information and less text to make it easier for tenants where English is not their first language, or who may have literacy problems. Allow tenants to describe their repair more clearly and accurately using diagrams or pictures. ( Wulvern Housing enables tenants to identify where and what their repair is using the ability to highlight the repair using a mouse, identifying the location of the repair. | Diane Thompson | 2014-02-01 | This will be part of the new system , part of a system called Repair Locator which is similar to what the hub has. It is very visual.
Social Media Increased Use
| 34 | Website Improvements |  | Change the wording on the current website , making it clear that by choosing which days tenants prefer an operative to call, doesn't constitute a definite appointment. ( on the "Report a Repair" link it currently says "arrange an appointment with our team." which is misleading.) The website should also be updated to include Saturday and evening preferences, as well as the current weekday, morning and afternoon slots. Alternatively, allow tenants to report repairs, view available appointment slots and book live through the Tenants Portal. | Diane Thompson | 2014-02-01 | This is is captured in the new system We are unable to implement on the exitsing system but we will amend the website as mentioned By November 13. Howver the new system will allow a live solution to allow real interaction.
| 35 |  |  | Introduce online tracking software either by using "See My Data" or by entering repair reference/job numbers via the Trust's website, so that tenants can view details of their repairs and track the progress of repairs operatives so that they know roughly when to expect them to arrive to do the job and make sure they are at home. | Diane Thompson | 2014-02-01 | This is a feature of the new system that operates through a Tenants Portal allowing much more interaction between tenants and THT.
| 36 |  |  | Include Completion dates of repairs in "See My Data" or equivalent system , so that staff and tenants can monitor the performance and satisfaction with repairs and check whether they are being carried out within target response times and appointments are being kept, Enabling archiving of repairs over 12 months old. | Diane Thompson | 2014-02-01 | This is a feature of the new system that operates through a Tenants Portal allowing much more interaction between tenants and THT. The front end of this system will be simple and easy to use.
| 37 |  |  | Encourage tenants to post comments saying how satisfied they are with their repairs using the Trust's Face book and Twitter pages. | Diane Thompson | 2013-11-01 | The Service will do a campaign through pulse, at events and with operatives to promote, we will offer incentives like prize draw for commenting.
| 38 |  |  | Allow staff to give feedback on how they think he system is working and identify any faults or problems they may experience, so that they can be rectified, preventing the need for them to work around any software problems. | Diane Thompson | 2014-02-01 | Testing and Training with staff is happening now , allowing feedback and changes but more formal training is due to take place between December and January.
| 39 |  |  | Make sure staff have adequate training and allow them enough time to familiarise themselves with the new system, before going "live". | Diane Thompson | 2014-02-01 | Testing and Training with staff is happening now , allowing feedback and changes but more formal training is due to take place between December and January.
Feed back and Consultation | 40 | More effective questions for surveys | Change of questions asked in Voluntas Survey | Change the types of questions asked in post transactional and add extra questions in the Star surveys, so that they are more specific about the repairs experience, rather than focussing on customer service and service delivery.E.g. Were you satisfied with the length of time you waited for the appointment ? Was the repair carried out promptly, or did the repair operative have to return another day with the materials? Instead of asking whether the operative was polite, or if the tenant is satisfied with the completed repair; determine if the tenant was satisfied with the journey to get their repair completed, were there any unnecessary delays , due to lack of time or materials for example. | Andrew Pearson | 2013-09-01 | Questions for 13/14 Voluntas Survey Year have new questions that the QIP have approved. We will capture the point about giving the option not to be contacted in the new system. We will also look at what the hub can do now. Customer Satisfaction is to be looked at more holistically from a Landlord perspective.
| 41 | Increase surveys taken | Increase Number of Questions asked. | Introduce recorded phone surveys, which are automatically raised on completion of each repair. This would improve the the response rate and give the Trust a better idea of the types of problems tenants are experiencing. | Andrew Pearson | 2014-04-01 | Agreed with QIP that would not be value for money to survey every repair and that instead we would look at increasing the number that Voluntas asks per month from 100 - 150 subject to 14/15 Budget. I shall also look to include an option through the Big One and with Voluntas, the chance for tenants to Opt Out.
| 42 | Increase ways of getting feedback | Issue Diaries to Properties CAG | Introduce Repairs Diaries for tenants who are willing to give feedback in this way, so that the Trust gets an overall view of the Service, what needs to be improved, what works well, over a period of time ( e.g a year) | Andrew Pearson | 2013-09-01 | Need to agree with Properties CAG, would look to do agree in September 13 and start in January 14.Will ensure a wider range of people to reivew this, to take into account various disabilities, language, and literacy problems.
| 43 | Updated Handbook | Updated Handbook | Publish an updated version of the Repairs Handbook, informing tenants of all the changes relating to the repairs service, such as weekday, evening and Saturday appointment slots. | Andrew Pearson | 2014-02-01 | To investigate different ways of delivering the Handbook, will review and consider people with disabilities, language and literacy issues.
| 44 | Interim information | Pull out Booklet in Pulse | As an interim measure consider including a pull-out booklet in Pulse, until an updated Repairs Handbook can be published. | Andrew Pearson | 2013-11-01 | Will produce a basic pictorial guide to most common issues and explain when the fuller version will be issued.
| 45 | List of Jobs and Rechargeable Repairs | List in Pulse and also become part of sign up process. | Tenants should also be given a list of jobs and rechargeable repairs that they are responsible for as part of the sign up process. | Andrew Pearson | 2014-02-01 | Use Pulse and to be part of the Sign up Pack.
| 46 | Top Tips for Tenants in Pulse | Quarterly Updates in Pulse | Include regular articles in Pulse called "Top tips for tenants by tenants", giving handy hints and tips, showing tenants how to carry out minor repairs and maintenance to their properties. | Andrew Pearson | 2013-12-01 | The QIP recognise that the Repairs Service already have done this in the past with cold weather etc.To look at simplifying the information given from the point of view of a complete novice, rather someone used to doing DIY. Cartoon like information to be considered. Also to consider geting tips from tenants and crediting them in Pulse.
Stores | 47 | Include all Regeneration Works Materials in Stores | Robust System in Place in Stores | New Stores solution is due by April 14. The Big One will also assist with this. | Andrew Pearson | 2014-05-01 | The QIP recognise that the Repairs Service already try to do this but the procurement process will enable us to address this more formally. We will also look to standardise some products. | New stores opened January 2014, Travis Perkins were successful and we have recently started to insource much of the decent homes kitchens and bathrooms programme from Regen, all this extra regen material is purchased directly through TP
| 48 | Bulk Purchasing | Bulk Purchasing In Place within In House Stores Solution. | Buy materials in bulk where this could reduce prices, evaluate and change how stock is re-ordered and the current length of delivery times, compared with what other suppliers are offering, similar to the arrangement the Trust now has with Permador , who now deliver UPVC doors by express delivery, reducing the turnaround from 4 weeks down to 10 days. It may also improve VFM if it was possible to bring stores procurement in-house. If the Trust do continue to use Buildbase, when their contract comes to an end in November 13, negotiate new contract terms regarding delivery times. | Andrew Pearson | 2014-02-01 | This is addressed by Buildbase at present, but will include it as a consideration as part of the procurement process, we plan to award the new contract on 1st November 2013.
| 49 | Consider appropriate KPI's attached to new stores solution. | Performance KPI's in place if we have in house stores solution. | Monitor delivery times , overtime and costs relating to supplies. | Andrew Pearson | 2014-05-01 | The QIP recognise that Builbase have these KPI's in place with Buildbase and they will be an integral part of the new contract. The New KPI's will be shared with the QIP.
| 50 | Updated Policies | Approved Policies | Update, sign off and publicise all Trust policies to do with repairs on the website and in any future repairs handbook, e.g. responsive repairs, recharges and compensation, so that tenants are aware of what repairs they are responsible for themselves and that they are entitled to compensation if inconvenience is caused when repairs are not carried out correctly, or if appointments have not been kept. It is also important that these policies are able to be signed of at Director level. | Andrew Pearson | 2013-09-01 | All Repair and Void Service Policies have been considered at the last two Property CAG Groups ( May and June) They all will be presented for approval at Delivery Dierectorate Management Team Meeting on 24th September 13.
Policies
| 51 | Easily understood Policies | Revised Compensation Policy | QIP also feels that any policies need to be easy to read and can be clearly understood by tenants. City West have published a very simple, yet comprehensive compensation policy , which appears on their website | Andrew Pearson | 2013-09-01 | All Repair and Void Service Policies have been considered at the last two Property CAG Groups ( May and June) They all will be presented for approval at Delivery Dierectorate Management Team Meeting on 24th September 13.
| 52 | Well Communicated Policies | Annual updates on repairs policies in Pulse and on Website. | Publish an annual programme of Pulse updates on repairs policies and tenants responsibilities. | Andrew Pearson | 2013-12-01 | To start in Winter Pulse 13 and then annually. | All repairs policies are now fully complete and available through a variety of methods
| 53 | Introduce penalties for THT when appropriate | Clear penalties as part of Compensation Policy. | Introduce set amounts for missed appointments, poor workmanship, (E.g. £10, £15 etc.) instead of awarding goodwill payments, paid at the discretion of Trust staff. | Andrew Pearson | 2015-08-01 | As part of the BICB project, go live in August 15, THT will record the missed appointments either by THT staff or the custoemr. Once this intelligence is known we can form the No Access Policy that will be consulted on and a draft presented to QIP. We will also look at non - monetised compensation where possible as part of a compensation policy, ie, Handyfix vouchers etc. All this to be consulted on with the Property CAG and QIP.
Asset Management | 54 | Annual Maintenance Programme | A Programme of Annual Maintenance Inspections | Introduce a more proactive approach to repairs and carry out Annual Maintenance Inspections. This would reduce the need to carry out 5 year cyclic programmes. This would highlight and identify repairs before they escalate into larger, more costly repairs, where contractors are more likely to be needed to do the work. | Diane Thompson | 2015-08-01 | As part of the knowledge of customer contributors and enablers, a pilot has been completed on visiting 20 customers who heavily use the service. This information is being evaluated as to whether an annual maintenance inspection should be introduced. Also a report is being generated via GIS of the users of the service to see if areas should be targeted.
| 55 | Introduce a Planned Maintenance Programme which would be responsible for general property maintenance. | A Planned Maintenance Programme. | Introduce a planned maintenance programme which would be responsible for general property maintenance. This could be carried out as part of a batched programme or a dedicated workforce, who are responsible for things like clearing out guttering on an annual or bi-annual basis. | Diane Thompson | 2013-10-01 | As the Repairs, Voids and Regeneration team are joining together through the Focus Programme, this is actively happening now.
Incentives | 56 | Introduce Incentives | Introduce a Tenants Incentive Scheme | Introduce a scheme which encourages and rewards tenants who take care of their homes, keep repair appointments, carry out minor repairs themselves, are not in arrears, cause ASB problems and keep tidy gardens. Those tenants that do qualify for the scheme receive benefits such as reduced response times for routine repairs. Those tenants that don't qualify have to wait longer and in some cases , such as severe rent arrears, we would review their services in line with legal advice. | Lauretta Rothery | 2014-10-01 | Incentives are being looked at as a bigger project that includes all tenants.
Note on I46: Diane Thompson:
Note on I74: Diane Thompson:
Note on I84: Diane Thompson:

## Compatibility Report
Compatibility Report for Repairs and Voids Service Plan 13.14.xls
Run on 25/03/2013 17:34
The following features in this workbook are not supported by earlier versions of Excel. These features may be lost or degraded when opening this workbook in an earlier version of Excel or if you save this workbook in an earlier file format.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 43 | Excel 97-2003