## QIP - GM Action Plan
Detail of Recommendation | Manager Reponse | Proposed Action | Target Date | Progress
1. All customers to be informed of the service specification for Grounds Maintenance and the resulting service charge. For example, customers could receive this information with the service charge letters. | The specification is available on the Trust's website and by individual request but it has not been sent to every customer who pays a service charge. It would be beneficial for the customer to receive an explaination about their grounds maintenance service charge and timing this with the service charge letters is both efficient and effective. | Prepare a 'Guide to your Grounds Maintenance Service Charge' to accompany the rent service charge letters on a yearly basis. Service charge letters are sent each year inbetween February and March. To make this information tailored to individual customers is highly time consuming and considering the level of queries relating to the charge is low, it is more efficient and effective for each customer to recieve an 'FAQ' sheet with an individual map identifying their particular grounds maintenance area. This document will be shared with the QIP prior to circulation. | 2016-03-01 | Start planning in Jan 16
2. More concise and eye catching information highlighting the main points should be supplied on the notice boards. This information should signpost customers to more detailed information if they are interested (e.g a phone number, website, or scheme manager). | The Trust can provide relevant, concise information in the communal areas of the independant living schemes quickly. This information will help those customers who wish to know more and ensure that they know where to go for it. Lowrise and Highrise flats each have a notice board, however, the way that we use this space is being reviewed. It will take longer to implement the same service as above in this case. | Prepare a 'What to expect from you're grounds maintenance service' flyer with relevant signposting information. The information for low-rise and high-rise flats will be developed and implemented as part of the caretaking improvement plan which will be developed with customers following the appointment of an Estates Manager. This document will be shared with the QIP prior to circulation. | Sheltered Schemes- October 2015 Low-Rise & High-Rise- Mar 16 | Document now approved and circulated to all blocks and IL schemes 03.08.15
3. Consider the use of Ground Maintenance champions to be appointed where possible as a spokesperson for the customers of each independent living scheme and estate area and to assist the service to engage and communicate with customers. | Over the last 6 months The Trust has worked closely with customers to move towards an in-house service and will continue to do so if/when more of the service is managed in house. This recommendation focuses on the ongoing monitoring of the contract by customers. It is agreed that aiming to recruit one green champion in each independant living scheme is a good place to start engagement. | Work with the customer insight team to set up a 'Green Inspectors' Pilot Scheme beginning with the Independent Living Schemes. This project relies on the appointment of the Customer Insight Manager. Make considerations for extending the pilot scheme if successful. | 2015-10-01 | Awaiting appointment of customer insight manager.
4. Develop an effective monitoring system for GreenFingers and CleanStart that enables the Trust to respond quickly to issues identified. For example, this could include a monthly quality check. | Since appointment in April 2015, the estates lead now undertakes a weekly analysis of complaints and comments on the service to ensure that any common themes are resolved. Customers are not involved in this but a customer perspective would be beneficial to improve service. | Review Grounds Maintenance complaints quarterly at Complaints Review Panel with at least 2 customers with the aim of learning from complaints to improve the service. | 2015-10-01 | Meeting is monthly. First meeting took place 30th July 2015. Outcome- meetings to be ongoing with improvements to be put in place to the service.
5. All complaints whether received directly to the trust or through GreenFingers could be monitored and acted upon to improve the service. Analyse complaint information to improve the service. Provide feedback to customers on how the Trust has used complaint information. | THT complaints procedure requires us to respond to individuals on the outcome of their complaint. In addition, Pulse can be used as a regular feature, simularly to the 'you said, we did' article, to feedback any improvements that we make as a result of customer feedback. | Set up a regular feature for grounds maintenance in pulse and use it to feedback from the complaints review meeting and any other improvements made from customer feedback. | 2015-10-01 | Discussed with communications department. July pulse is a short edition to include information on the garden competition and September pulse is a special birthday edition. Starting in January, there will be a regular feature to feedback on what customers have said and what we have done about it as well as advice for gardening in the winter season. This will give time to explore feedback mechanisms and green inspectors which will feed into pulse.
6. Develop a range of methods to involve customers in the co-design and co-delivery of services including feedback loops to update the customer. For example scheme and area representatives, tenant panels and neighbourhood consultations. | The grounds maintenance contract was agreed in 2010 and was co-designed with customers. As the service comes inhouse on a phased basis, co-design and co-delivery will be ongoing in the form of focus groups for each new area of expansion by the CleanStart team. Additionally a complaints review panel (see point 5) and a green inspectors scheme (See point 4) will enable customers to work with the Trust to co-deliver the service. | Introduce new involvement methods of Green Inspector (recommendation 3)& Complaints Review Panel (recommendation 4) & provide feedback to the customer in Annual service charge letters,(recommendation 1) posters on notice boards (recommendation 2) Pulse (recommendation 5) and on the website and social media. | Oct 15 | Update as per columns above.
7. Develop a range of methods to obtain feedback on the service and inform customers how this has been used to improve the service. For example, use of surveys, text messaging and scheme and area representatives. The current block champions’ model is a good example of how feedback can be obtained. | Greenfingers send out feedback cards to assess satisfaction on each of the sites that they maintain but the Trust does not pro-activley seek feedback on the service. The weekly analysis of complaints and compliments is retrospective. The green inspectors scheme and complaints panel will give us links to customers to engage with them for more feedback, however, there are other ways that we can take a wholistic view of the service, such as use of surveys and text messages. | Develop a method of obtaining wholistic feedback working with the business intelligence team to align the task with other methods by which the trust already obtain feedback e.g STAR survey. Work with the customer intelligence officer to identify the right way of going about this. Discuss options with QIP before making a decision and circulating. | 2016-03-01 | Current feedback methods are annual so not appropriate for regular analysis of the service.Carly Chadwick working with Natalie on replicating quarterly repairs telephone survey.