| SENATE SCRUTINY REPORT – SERVICES STANDARDS ACTION PLAN: |  |  |  |  |  |  |  |  |  | Period covered (from / to): |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | November 2009 to March 2011 |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 1.Customer inspectors should monitor the service provided by Salford City Councils Environmental Services quarterly | I | 01/04/09 | 31/03/10 | Amy Welsby | Estates Maintained to a high standard | Increase in customer satisfaction SLA currently monitored by Cleaner/Greener and members of CG SSP. Targeted attendance of Customer Inspectors at Rate Your N’hood Walkabouts in scope | N/A | N/A | Customer Inspectors now at rate your neighbourhood walkabouts Learning and Diversity Committee Cleaner/Greener SSP |  |
| 2. Salix Home should set up an inspection regime of low rise in accordance with its practices regarding high rise | S | 14/12/09 | 31/03/10 | Colin Mannion | Clean Communal Areas | Increase in customer satisfaction Weekly Inspections. New Cleaning Services Supervisor Launch of new in-house Clean Team 01.03.10 | N/A | N/A | Senate Customer Access and Involvement Panel Learning and Diversity Committee |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 3. Salix should carry out an audit of all blocks to ensure that superintendants emergency contact details are available and visible to all. | S | 14/12/09 | 01/02/10 | Sam Tindale | Customers will know what service to expect from the contact centre and be able to monitor their performance | Contact centre PI’s such as Customer Satisfaction Time to answer a call etc. All ‘caretaking supervisor’ details to be displayed in public areas; photo ID, phone number, brief list of duties. | N/A | N/A | Performance Committee Senate and SSP’s |  |
| 4. A policy needs to be drafted to ensure that an estate walkabout is conducted with customer representative and key stakeholders, and the information be reported to the relevant SSP | S | 01/04/09 | 31/03/10 | Colin Mannion | Improved Service Delivery | Increase in customer satisfaction. Pictorial Guide. Programme of estate walkabouts on web. | N/A | N/A | L&D Committee Cleaner ,Greener SSP |  |
| 5 Salix Homes should introduce a policy with regard to Car Parking. | S | 01/01/10 | 31/03/11 | Warren Carlon |  | Increase in customer satisfaction. Safer Neighbourhoods Team currently managing a pilot at Friars Blocks | N/A | N/A | Cleaner ,Greener SSP Safer SSP L&D committee |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 6. Salix Homes should strive to meet 5 day response times following correspondence, as per industry levels of good practice | S | 01/0110 | 31/03/10 | Daryl Stonebank | Customers are kept informed of how their issue is being progressed | Increase in customer satisfaction | N/A | N/A | EMT, Performance Committee Senate CI&A SSP |  |
| 7.Information regarding Choice Based Lettings should be available via the website, as well as being on display in all customer access points | S | 01/12/09 | 31/01/10 | Pam Roberts | Improved access to services Increase in customer satisfaction | Website gives details on Salford Home Search and Pinpoint with links to these sites. More information to be displayed in all customer access points | N/A | N/A | Empty Properties SSP |  |
| 8. Lettings and Allocations Service Standard 5 should actually be in the remit of the Cleaner / Greener SSP | S | 01/12/09 | 14/12/09 | Pam Roberts/ Colin Mannion |  | Increase the. Photo ID, contact details of all caretaking supervisors to be displayed in all public areas. Available to support accompanied viewings with EP Officers. | N/A | N/A |  |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 9. Service Standards pertaining to Sheltered Housing should be monitored by the Sheltered Tenants Forum | S | 04/01/10 | 31/03/10 | Helen Thorpe | Sheltered customers have a clear role in regulating performance and ensuring they are receiving the standard of service they have been promised | N/A | N/A | N/A | Empty Properties SSP |  |
| 10. There should be an updated version of the Leaseholders Handbook produced | S | 01/08/09 | 31/12/09 | Helen Thorpe | Information available to all leaseholders about their rights and responsibilities in the same format as that received by tenants | Information on website and sent to each leasholder |  |  | Neighbourhoods Committee Better Neighbourhoods SSP |  |
| 11. All rent letters should be dated | S | 01/12/09 | 7/12/09 | Sharon Simmonds | Customers are aware of when letter was sent | Dates are on rent letters | N/A | N/A | Completed |  |

| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 12. There is no evidence that a County Court Judgement is followed by any enforcement action other that to seek a repossession order. As enforcement actions are varied, and can be both cheap and effective, this neglect of them appears strange. | S | 4/01/10 | 31/01/10 | Sharon Simmonds | Action taken is the most appropriate to reflect the customer’s individual circumstances | Enforcement Actions reviewed & new methods implemented if appropriate. Number of enforcement actions of various types taken | N/A | N/A | Income Management SSP |
| 13. Feedback and monitoring data MUST be passed to the relevant SSP at all times to facilitate constant up-to-date information, and thereby prevent failures in the provision of the service to customers promised by Salix Homes. | S | 01/12/09 | 31/03/10 | Rebecca Chambers | Accessible performance information available via the website and feedback and service standards reports provided to all SSPs | Service standards (all) |  |  | ALL SSP’s |