| SENATE SCRUTINY REPORT – ‘COUNT ME IN’ ACTION PLAN: |  |  |  |  |  |  |  |  |  | Period covered (from / to): |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  | September 2010 to March 31/03/11 |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 1. Review current governance arrangements for customer involvement to achieve value for money | S | 17/08/10 | 30/06/11 | Margaret Connor | Customers will be able to influence service delivery | Number of customers involved Actual cost savings | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 2. Review customer involvement strategy to reflect the scrutiny of ‘Count Me In’ and incorporate the hard to reach strategy | S | 01/01/10 | 31/03/11 | Margaret Connor | Customers will be able to influence service delivery | Number of opportunities Number of customers using menu 10% increase in ‘need to reach’ customers | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 3. Review role of Salix 600. | S | 01/01/10 | 31/03/11 | Ken Morton | Salix 600 will be used effectively and members will be able to influence service delivery | Number of customers actively getting involved in their method of choice | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 4. Relaunch Salix 600 | S | 01/04/11 | 30/06/11 | Ken Morton | Customers receive a consistent service and receive appropriate information to influence service delivery | Number of activities Number of responses per activity | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 5. Develop the creative hub to celebrate achievements and diversity of Central Salford | S | 01/-01/11 | 31/03/12 | Ken Morton | Customers will be able to record their satisfaction in a variety of methods | N/A | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 6. Embed the use of the central diary to plan and deliver customer involvement opportunities | S | 01/01/11 | 31/03/12 | Ken Morton | Maximise the opportunities for customers to get involved and prevent duplication | Number of events Number of customers attending | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 7. Embed the use of customer impact assessments to capture effectiveness of customer involvement | S | 01/01/11 | 31/03/12 | Ken Morton | Effectively deliver opportunities for involvement that achieve value for money and make an impact | Number of outputs Number of customers attending | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 8. Explore the feasibility to incorporate community development within the job role of officers or introduce a community development role | S | 01/01/11 | 31/03/12 | Jonathon Drake/ Margaret Connor | Customers encouraged and empowered to get involved in their local community and wider involvement structure | Number of opportunities delivered Number of customers getting involved | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 9. Align the job description of Neighbourhood Officer and Customer Involvement Officer | S | 01/01/11 | 31/03/11 | Jonathon Drake/ Margaret Connor | Customers receive a consistent service | Increase in customer satisfaction | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 10. Monitor effectiveness of Neighbourhood Team Leaders and Officers. | S | 01/01/11 | 31/03/12 | Jonathon Drake | Customers receive a consistent service | Increase in customer satisfaction | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 11. Explore the provision of a youth co-ordinator role | S | 01/01/11 | 31/03/11 | Sue Sutton/ Margaret Connor | Ensures activities for young people are available and co-ordinated | 25% increase in the number of young people involved | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 12. Develop and deliver a programme of youth activities and involvement opportunities. | S | 01/01/11 | 31/03/12 | Ken Morton | Ensures young people have an opportunity to influence service delivery | Increase in customer satisfaction Number of young people getting involved | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 13. Develop and support a Young Senate | S | 01/01/11 | 31/03/12 | Ken Morton | Ensures young people have an opportunity to influence service delivery | Number of scrutiny activities Number of recommendations implemented | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 14. Explore the opportunities Northgate offers to record customer involvement activities or integration with TP tracker. | S | 01/01/11 | 31/03/12 | Ken Morton | Ensures effective delivery of involvement opportunities that deliver value for money and maximise impact | Number of customers who get involved Number of activities offered Number of outcomes | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 15. Engage the most appropriate method for recording customer involvement | S | 01/01/11 | 31/03/12 | Ken Morton | Effective recording of involvement activities | Number of customers who get involved Number of activities offered | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 16. Review the current allocation of points for customer involvement and develop an appropriate scheme of recognition | S | 01/01/11 | 31/03/11 | Ken Morton | Commitment of customers is recognised | Number of points Number of awards | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 17. Implement scheme of recognition for involvement | S | 01/04/11 | 31/03/12 | Ken Morton | Commitment of customers is recognised | Number of points Number of awards | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 18. Review the need for a centralised administration support for customer involvement and achieve value for money | S | 01/01/11 | 31/03/11 | Margaret Connor | Ensures consistency of paperwork and recording of activity | Increase Customer Satisfaction | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 19. Implement the findings of the review for a centralised administration support | S | 01/04/11 | 31/03/12 | Margaret Connor | Improved and consistent service delivery | Increase Customer Satisfaction | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 20. Review the support for tenant and resident associations to ensure consistency and inclusivity | S | 01/01/11 | 31/01/11 | Debbie Broadhurst/Neil Matthews | Improved and consistent service delivery | Increase in number of events taking place Increase in number of residents attending events | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 21. Implement the findings of the review for support to tenant and resident associations | S | 01/02/11 | 31/03/12 | Debbie Broadhurst/Neil Matthews | Improved and consistent service delivery | Increase in number of events taking place Increase in number of residents attending events | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 22. Develop and deliver a programme of intergeneration activities | S | 01/01/10 | 31/03/11 | Ken Morton | Ensures barriers to getting involved are removed Offers opportunities to share skills | Number of activities delivered Number of young people getting involved Number of older people getting involved | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 23. Effectively publicise customer involvement opportunities and their outcomes | S | 01/01/11 | 31/03/11 | Neil Matthews | Ensures wider customer body are aware of opportunities and their impact on service delivery | Number of events publicised Number of outcomes | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 24. Develop and promote a buddy role to encourage customer involvement | S | 01/01/11 | 31/03/12 | Adrian Palmer | Empowers customers to get involved | Number of customers who access scheme | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| Action | Organisational Objective | Start Date | Completion Date | Lead Officer | Benefits to Customers | Measures/ PI's that apply to this action | AC Reference | Project Reference | Milestone Progress Reports To: |  |
| 25. Effectively work in partnership with contractors to maximise opportunities for involvement | S | 01/01/11 | 31/03/12 | Ken Morton | Ensures customers have a range of opportunities to influence service delivery | Number of opportunities Number of customers accessing opportunities | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 26. Review Articles and memorandums to remove any reference to a federation of tenants | S | 01/12/10 | 31/01/11 | Rob Wakefield | Reflects current involvement structure | N/A | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 27. Where appropriate consider alternative methods of translation | S | 01/12/10 | 31/03/12 | Daryl Stonebank | Consistent service that delivers value for money | Improved customer satisfaction | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |
| 28. Explore the appetite for and benefits of a formal learning event for other landlords and their customers | S | 01/01/11 | 30/06/11 | Margaret Connor | Allows customers to share their experience for the benefit others | Number of events Number of delegates | N/A | N/A | Learning and Diversity Committee Customer Panel Senate |  |