Appendix 2 – Action Plan

Draft

TEES VALLEY SCRUTINY PANEL

GROUNDS MAINTENANCE KEY RECOMMENDATIONS ACTION PLAN

| Item Code | Recommendation | Actions | Responsible Officer | Completion Date | Progress Status |
| --- | --- | --- | --- | --- | --- |
| A. | Rewrite the TV GM rota to use towns/places which are correct and familiar to tenants | Check Town and Scheme names against official listings to ensure they conform. | D. Ayton GM Supervisor | March 31 2013 | IN PROGESS |
| B. | Re-formulate rota to ensure area’s are programmed in that are close to each other | Re-arrange the route of the teams visits to ensure efficient travel & customer options. | D. Ayton GM Supervisor | March 31 2013 | IN PROGESS |
| C. | Give clear information on the published leaflet of winter/summer service specifications | Arrange for the 2013/14 published program leaflet to include a section on service specification, Winter & Summer. | S.Sykes GM Manager | March 31 2013 | IN PROGESS |
| E. | Suggest Supervisor should carry out regular spot checks | Introduce a formalised check sheet which the operatives and management use for logging work visits and subsequent checking of work. | S.Sykes GM Manager | Jan 31 2013 | IN PROGESS |
| F. | Suggest Customer Care training is given to carried out for all GM operatives | 6 Operatives already have a City and Guilds Certification in Customer Care and all operatives have now attended an in house Customer Care course. | D. Ayton GM Supervisor | Jan 31 2013 | COMPLETE |
| Item Code | Recommendation | Actions | Responsible Officer | Completion Date | Progress Status |
| G. | Call Centre staff to receive training on Grounds Maintenance on what tasks are ongoing throughout the season | GM Mgmt to arrange to carry out a presentation to the `Call Ctr’ | S.Sykes GM Manager | April 2013 | IN PROGESS |
| H. | Call Ctr staff to be informed of up to date changes in the Grounds published schedule | Not actionable as outlined The nature of the grounds tasks are such that some changes or delays delays in programmes cab be inevitable given weather and ground conditions. Suggested that contact with the Call Ctr is undertaken only where a protracted delay e.g. more than 5 working days. | S.Sykes GM Manager | N/A | N/A |
| I. | Grounds Maintenance question to be added to the STAR survey and surveys twice a year on resident satisfaction with grounds. | Draft question on Grounds Maintenance to be added to the STAR survey. | S.Smith Business Improvement Manager | July 31 2013 | IN PROGESS |
| J | Benchmarking should be current and regular and comparisons should be made with other like sized Housing providers. | This is an area being reviewed through the wider Value for Money framework including local benchmarking groups. Also links with recommendation I above. | S.Smith Business Improvement Manager | July 31 2013 | TO REVIEW |
| K. | Service Charges need to be actual cost , itemised and transparent to enable and understanding | Not actionable as outlined This for further discussion with the panel. It is believed that this is currently satisfied to a reasonable level. The basis of the service charge is to give a fair `Value for Money’ charge across a range of services considering the level, timing and cost of those services are at least in line with the market prices. | S.Sykes GM Manager | N/A | N/A |
| L. | Complaints reported on site should go through the failure and complaints system | Ensure the new formalised check sheets are used to pass on complaints and compliments to the Call Ctr team via the team members and the Supervisor | D. Ayton Supervisor | Feb 28 2013 | IN PROGESS |
| M. | The IT system should recognise site/schemes and not just individual issues | To review The IT system does not currently match to this level of detail in all cases and this may not be fully practical or economic to implement. | S.Sykes GM Manager AM Lenagh Group Head of ICT | N/A | TO REVIEW |
| N. | Grounds Maintenance attendance at Toolbox Talks should be more consistent | Training Officer to invite Supervisor and Grounds Staff to all relevant `Tool Box’ talks. | D Ayton Supervisor | Jan 31 2013 | COMPLETE |
| P | Work carried out on site should be properly recorded on formal records & should include time on site, work comp and comments and then signed off by the manager | Requested information to be included on the formalised check sheet | D Ayton Supervisor | Feb 28 2013 | IN PROGESS |
| Q | A COSHH manual should be kept in the vehicle and First Aid training given to all to allow knowledge in each of the teams | Copies of COSHH manual to be located in each vehicle & First aid training to be carried out. | D Ayton Supervisor | Feb 28 2013 | I IN PROGESS |

| General Management Activities |  |  |
| --- | --- | --- |
| D. | Address the length of down time involved in replacing employees on sick leave. | Fabrick Group has an absence policy and managers operate within this policy. There is no significant variation in sickness levels relevant to this service. |
| O. | Operatives should have access to a personal development plan for their training needs | Fabrick Group has an appraisal and personal development policy and managers operate within this policy. This area of staff performance and review is also scheduled on the Internal Audit plan for 2013/14 (across Group, not specific to GM services). |