## lead officer
Lead | No | area | Key Recommendations and areas for improvement | Managers Comment | Officer | Planned Actions and Outcomes | Milestone (date) | Implementation date | Progress since last meeting
Andy | 3.18 | DI | The websites allow for anonymous entry of complaints/ASB about the local area. There could be more publicity and promotion of this as it can act as an early warning system for landlords and prevent people leaving due to ASB | Agreed to promote the existing ability for tenants to report ASB anonymously across group | Gilly Marshall | Develop communication plan in a group wide context |  | 2014-08-01
Andy | 3.11 | E | Consultation with customers in Sheltered and Extra care schemes to be carried out about heating levels (and control of this) in the communal areas as many complain it is too hot and they have no control over the temperature | a) consultation within the schemes about heating levels (Andy) b) Implement proposals following the consultation (Mike) c) undertake investment works by March 2015 | Andy Powell, MK | Consultation is straight forward in terms of understanding customer views . Issues will arise with regard to planning into either maintaince or assett management plans | consulatation undertaken by October 2014 | 2015-03-01 | None AP to raise with Jack Dodds re consultation and with assett management
Andy | 3.13 | N | Customers need to feel empowered to collectively support landlords in enforcement action against ASB, this would make a useful project to investigate for the VIPs. | Scrutiny group to meet Gilly Marshall to explore options and possible VIP project | Gilly Marshall |  | 2014-07-01 | 2014-12-01
Andy | 3.12 | N | HH patch sizes to be equalised with the TH patch sizes, or be able to refer complex cases to a group-wide Tenancy Support team | All patches will be reviewed as part of the neighbourhoods review.We are also exploring how we can work with Thirteen's Care and Support team to acces support services. | Andy Powell | AP to review the methodology for fixing allocations between Neighbourhood teams | 2014-07-01 | 2014-07-01
Andy | 3.11 | O | Services offered to older and vulnerable customers in HH should be offered to customers from all landlords across Group | Subject to the development of the Older Persons Housing Strategy and local commissioning variations and the views of customers outside Hartlepool | Andy Powell, Paul Noddings | Develop Older Person Housing Strategy | Scope of Strategy to be agreed by July 2014 | 2014-12-01
Andy | 3.11 | O | More promotion of the benefits of moving to sheltered accommodation rather than moving out of a 3 bed housing into a care home, and moving encouraged before the stage when they can no longer be accepted for sheltered accommodation | Marketing and review of the accomodation for older persons to be included within the Older Persons Housing Strategy | Andy Powell |  | Scope of Strategy to be agreed by July 2014 | 2014-12-01
Andy | 3.11 | O | The Customer involvement action plan that was produced in 2013 for Extra care and sheltered accommodation in HH to be implemented | Specific resource for this identified within the CI structure for a CI plan across the group for older people | Andy Powell |  | 2014-09-01 | 2014-12-01
Andy | 3.25 | T | Develop customer profiling to link hot spots of tenancy turnover to the sustainment needs and to target tenancy sustainment activity to these hot spots | This layering of information is occuring via the sustainability model | NMs | Request that MA highlight this within the Sustainability Tool | Feedback from MA on achieveability June 14 | 2014-09-01
Chris | 3.14 | MEXT | Customer on the transfer list who have an arrears agreement should be able to be given the opportunity to catch up on a payment that they missed by being a sent a reminder, in order for them to stay on the list and not go back to week one | Flexibility and office discretion is required which reflects tenants circumstances but which still aligns to the need for customers to show a long term commitment to rent repayments prior to accessing the register. | Julie McNaughton | Agree training following recruitment into new roles to ensure consistency of approach. |  | 2014-10-01
Chris | 3.5 | MEXT | Transfer customers should be given at least 1 full working day to make arrangements prior to moving. If keys are given out after Thursday for transfer customers, the customer should not have to pay the week’s rent for their old home | This will need reviewing as part of the Empty Property review. Many team involved - had 2 meeting so far (30th June)from this we need an overarching strategy on where we are going. As part of this remit we will have task and finish groups with customers in August 2014 interested in all elements of tenancy management, lettings, finance etc. and we may be able to pilot some of the ideas before Dec 14 | Chris Joynes | Establish project team to review empty property management and timetable. Staff group already established. | First meeting to take place by July 2014 which will establish project plan | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.3 | NT | All new tenants be assessed for the Tenancy Support Service (group-wide) - only happens in Tristar. Also customers used to complete a risk of tenancy failure assessment at the bidding stage, this should be re-introduced across both landlords | The Lettings team are aligning processes and highlighting any good practices to include within this work and role across the Thirteen group. The group will explore the previous process as outlined and bring all working practices together. | Julie McNaughton | December 2014 Board - agree the Strategy. March 2015 implementation | 2014-09-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.3 | NT | Decoration standards and allowances should be brought together across group. A handyperson or decorating service should be considered across Group, either as a social enterprise or otherwise | To be reviewed as part of Empty Property Review. An Interim agreemet of 3 standards has been agreed 1 = DHS; 2 = DHS and decoration; 3 = DHS plus enhancements - Geoff Pryor working on a definition - categorisation of each void will be based on Patch manager decision of knowledge of area and lettability issues | Chris Joynes | Project team approach required to agree new approach to managing voids in a thirteen context | Agreed standard and decoration allowance to be in place Dec 14. Some piloting of ideas to Dec 2014. | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.3 | NT | Staff reminded to go through everything in the sign up pack, they give out lots of information but there may not be sufficient focus on money advice. | We are proposing to introduce joint/multi sign up approaches and possibly a pre-sign up which would include financial assessment/awareness session briefings. Current thinking is DVD which is already available but needs "Thirteen" branding. Also developing a unified tenancy agreement. Slight changes in this to go onto DVD | Julie McNaughton | Agree approach in a group wide context | 2014-08-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.25 | T | Ensure both landlords collect the same data on termination reasons and look at ways to incentivise customers to allow termination visits when people are looking to leave. Promote the benefits of security of tenancy and other rights, as a benefit for staying in our homes rather than leaving for the private rented sector | There is some consistency but limited to some extent by ICT issues. This will be resolved via IPACS implementation.Keen to have a tempate which can be interrogated. Terminaton reasons to be agreed by August 2014 and will collect it on an excel spreadsheet until IPACs in place. The procedures for termination visits and access incentives will sit under the policy, as will how we promote the benefits of being a Thirteen tenant | Chris Joynes | Review as part of IPACs implementation. | Agree approach following IPACs contract being awarded - October 2014 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.25 | T | Customers to be involved in any review of the Tenancy Policy under the Thirteen group, be consulted on affordable rents and fixed term tenancies and their impact on people choosing our properties or choosing to leave them | New Tenancy Policy needs to be developed in a Thirteen context and linked to the new strategic TeesValley local authority framework. 14 partner policy areas being joined together. Task and finish groups of tenants to be involved. | Chris Joynes | Policy will undergo a full Equality Needs Impact Assessment | New policy in place Dec 14 | 2014-12-01
Chris | MR14 | T | A customer who says they are leaving should be visited not just for repairs when the tenancy has ended, but immediately as notice is given by the patch manager to see if it is possible to support them to remain in their home. | Agreed. EH & TVH voids Task & Finish Group have agreed a new process i.e. the pre-termination inspection is carried out by the neighbourhood teams instead of the empty property team, as they have the local knowledge in terms of tenancy conduct and any issues that need to be addressed. The pilot is working well and it is anticipated that it will be rolled out Group wide in the next few weeks/months. Links to Support to Stay initiative and Neighbourhood Sustainability Pilots. Patch manager must now speak to everyone who is going to see if they can persuade them to stay | Neighbourhood Managers across Thirteen & Julie McNaughton | Discuss agreed approach | 2014-07-01 | 2014-11-01
Chris | MR15 | V | The minimum void standard should be increased to to compete with the private rented sector and give customers the best possible start in their new home. The homes should always be deep cleaned, so customers can move in with the minimum of effort. When in future the void standard is reviewed, it should incorporate decoration issues and customers to be involved in this review | On-going discussions are in place around minimum standard and our approach to empty property management. Further work is now required in a group wide context. The standard maybe linked to size/location to determine the standard. | Julia Kett | Project team approach required to agree new approach to managing voids in a thirteen context | 2014-07-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.2 | WP | The Welcome pack should be placed on the website and the information could be printed only for those who cannot access the website. Those customers who are dyslexic or struggling to read quickly, should be able to access the information in the Welcome pack through videos placed on our websites | Agree that this information should be available via the website once the welcome pack has been updated this will be progressed. We have developed a DVD that can be played in sections that covers the main information and requirements for their tenancy. The intention is to include this on the websites once it has been branded for all organisations | Julie McNaughton | Update DVD ensure branding is appropriate and make accessible via the website | 2014-09-01 | 2014-10-01
Chris | MR3 | WP | The Welcome packs should be more professional, simplified and some of the papers should be given at offer or viewing stage to ensure customers have a better understanding and information about their tenancy. New tenants should be asked to sign a checklist that they have been given and understood the contents | Agree that paperwork needs to be professional, simplified and consistent. There is a working group looking at the Welcome sign up pack. This will be streamlined to focus on the importance of the contractual agreement. The neighbourhood teams will take the rest of the information to the welcome visit. | Julie McNaughton | Discuss with colleagues across group and customers around Thirteen approach to the sign up process ensuring also that neighbourhood teams visit in the property within first week or two? | Discussion and agreed approach by July 2014 | 2014-10-01
Chris | 3.16 | WR | Flat should be offered to families with children to enable them to downsize, rather than to leave for the private sector | This was introduced within the allocations policy within the last review. This needs to be neighbourhood led as they need to identify suitable flats that would accommodate a family unit without causing any sustainability issues. Need to agree an approach - The neighbourhood team need to confirm suitability at the advertisement stage considering the neighbourhood and suitability. Patch manager must now speak to everyone if they are going to recommend a local lettings polic | Julie McNaughton | Training to be rolled out to the neighbourhood teams to ensure that suitable properties are advertised to allow families to bid. | When Neighbourhood Officers are in place they can influence the local lettings policies | Implementation will follow conversations with customers in the blocks/area from September 2014
Chris | MR13 | WR | The rules for allocations to change to allow those who can upsize and pay for this, to be able to do this. Staff should be trained to understand that the allocations policy allows those who can pay for 3 bed homes to upsize, even if they are under-occupying. | Allocations are via CBL sub regional scheme and customers do have some flexibility to upsize i.e. 1/2 bedroom need for individuals and couples; 2/3 for couple/single with one child etc. although priority goes to customers who have a need for the number of rooms indicated. These discussions do take place with customers. Discussion required around enabling single people to apply for properties much bigger than their needs on an area basis in particular where there is low demand but customers can afford to upsize. | Julie McNaughton | Establish a unified approach in a Thirteen context. We will advertise based on need and if cannot allocate then can offer to others. Needs implementation of the new officers and teams from September to ensure this message goes across all teams | August 2014. | September 2014 - all teams will be togather and be in the same message
Chris | MR18 | F | TH and HH to have a comprehensive solution to access furniture/white goods for new and existing customers. A conversation should be had with the customer when the home is viewed to enable the new customer to pay more on the rent for white goods, carpets, decoration or whatever a customer needs | On-going discussions are in place around minimum standard and our approach to empty property management. Further work is now required in a group wide context. A charge on the rent is not possible as Thirteen are unable to offer loans currently and would always look at partners i.e. credit unions who have this facility to support these types of requests around white goods/carpets etc. Financial inclusion and empty property teams will share information so that the customer is given the relevant information on viewing. This action links in with access to furniture for existing customers. | Julia Kett/Lisa Fearn | Further discussion required as part of service review on empty properties. Lisa to work through incentives like Smartbuys. Kay to develop the model with Lisa. Chris to work through with patch officers what under menu 3 of the void standard are the incentives that can be offered to applicants | Project outcomes to be agreed by August 2014 | Board will agree the strategy by December 2014 with March 2015 implementation | JK and LF met 30.5.14. The financial inclusion team will share info on credit unions and the empty property teams on second-hand furniture provision. JK will update LF on outcome of service review on empty properties. Funding will need to be identified to facilitate these type of loans for credit union members.
Chris | 3.9 | NT | The staff should explain to new customers the importance of taking meter readings and immediately informing the utility companies about the tenancy change | This should be standard practice. Note: we have entered into a partnership as part of a wider consortia (Mike Kay lead officer) with OVO Energy (proffered supplier). We are about to embark on a pilot in Middlesbrough where SMART meters will be installed in empty properties and the process will factor in meter readings and switching utilities to the preferred supplier, providing this is what the tenant wants. | Julia Kett/Neighbourhood Managers | This should be in place and reaffirmed following recruitment to new roles. Patch manager will have a converstaion with the incoming and outgoing teant to ensure they take meter readings |  | September 2014 - all teams will be togather and be in the same message
Chris | MR16 | I | Investment works not to be brought forward in a property when a customer leaves as this causes upset on the estate, when the former customer may have moved out due to delays in getting the work done | Links to the Empty homes strategy and void working party, need flexibility and consideration of the local circumstances. Need to work out what the patch officer can do to enable people to stay and how we ensure clear consistent message is communicated to the wider customer base of our approach | Mark Robson/Nik Turner | Agree approach, links to Geoff Prior's work on 3 voids standards and the timescales for this above. |  | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.1 | PT | Some work started in the involvement team to produce some short videos about what it means to have a tenancy however this was not completed. These should be completed and placed on the website | DVDs have been produced for new customers for tenancy induction purposes in some parts of the new Group. We would like to update these where applicable and extend the availability of visual material across all partner landlords. Need to link with the KYM project and develop short videos/DVD for Young People with the new Customer Invovlement Manager | Julie McNaughton and CIM | Task and finish group to be established to agree what videos and timescales. Need to understand what the Young People want to know - speak to colleges and those in later school ages | Will have DVD for September 2014 | 2014-11-01
Chris | MR34 | WR | VIPs to undertake an investigation into the offer made in the private sector and a separate investigation into those subject to the bedroom tax to be able to talk to them about the support they need. | Julie to work with Jonathan Cannon from CI team on a CSI project to her brief starting July 2014. | Julie McNaughton | CSI project for HH and TH to investigate PRS offer in July/August 2014 | August 2014. | 2014-12-01 | Mystery shopping to be carreid out in July on the Private Rented sector offer by CSI group
Kay | 3.12 | N | When estates are improved and demand goes up, HH and TH should increase positive publicity to remove the poor reputation of estates and make people proud of where they live | Agreed that a pro-active approach is needed | Kay Glew | Agree approach and implementation programme | 2014-08-01 | 2014-10-01
Kay | 3.1 | F | Thirteen group to negotiate with local Housing Benefit departments to assess the feasibility of all new tenants being able to access a furniture package, which is currently only available to those with support needs. | Depending on how the furniture schemes / furniture packs are set up, this can prove to be expensive for customers who move into work and stop claiming housing benefit so this initiative could work against our employability initiatives. Ensure the pre tenancy assesment clarifies who is vulnerable and can therefore access furniture on full HB | Lisa Fearna nd Julie McNaughton | Agree approach | 2014-09-01 | 2014-10-01
Kay | MR11 | MEXT | Customers who apply for an exchange or a transfer should do so through the Patch Manager who can discuss what might enable the customer to stay. Immediate visits should be carried out to see if the landlords can take action before they terminate their tenancy | Agreed that these visits will take place by neighbourhood teams although timescales around visits will need to be agreed. This will form part of the inspection visit to all tenants following a transfer application form or mutual exchange application being registered. This is to prevent losing tenants who may also leave the company through other landlords. | Neighbourhood Managers across Thirteen | NM/s to agree an approach to support customers who identify that they want to transfer/mutual exchange/terminate their tenancy | Discussion and agreed approach by July 2014 | 2014-08-01
Kay | 3.14 | MEXT | Staff felt mutual exchanges were costly due to the checks that needed to be done, so there was no benefit to the landlord to encourage it. Some staff do not know they work. Mutual exchanges should be supported, and staff should be trained to promote it | Agreed and this is a low cost solution. | Kay Glew/Andy Powell in TH and HH context | Pro-active discussion with Neighbourhoods teams and agree training programme following recruitment into new roles. |  | 2014-10-01
Kay | 3.14 | MEXT | Customers said they got no support to achieve a mutual exchange and they would rather see a member of staff employed to match the mutual exchange applicants, rather than waste money paying out on DHP. | The DHP scheme has been well supported by customers following a review of the scheme after 6 months. Neighbourhood officers will be responsible in a group context for mutual exchange process supporting customers with matching opportunities. It is felt that localised officers are better placed than having one dedicated officer. This has been passed to Neighbourhoods by The Contracts Team to deal with from start to finish | Neighbourhood Managers | Discuss approach following recruitment to the neighbourhood teams and ensure appropriate training is in place | Establish process following recruitment to teams- Sept - 2014 | 2014-10-01
Kay | 3.29 | MEXT | Vela’s most recent Mutual Exchange Policy to be placed on the websites of TH and HH | Agreed | Neighbourhood Managers | Add to website |  | 2014-08-01
Kay | MR12 | MEXT | Customers who need to move should be able to get support from a specialist person who can explore 2 and 3-way mutual exchanges and enable the move to release at least one of the customers from bedroom tax costs | This role would fit within the neighbourhood service. We would always want to pro-actively support and facilitate mutual exchanges as a low cost solution to meet customers rehousing needs | Neighbourhood managers | DF with colleagues to establish an approach in a thirteen context. | Discussion and agreed approach by July 2014 | 2014-10-01
Kay | MR6 | C | All contact with customers to include a review and updating of customer profiling information held. | TH and HH have sent out a full survey to customers to update their profile. Contact team should check telephone and profiling information during contacts. Once IPACs and mobile working in place, this will be more possible via neighbourhoods teams. Unlikely to be all staff at all contact but agree it is a priority. | Adele McLaren | To review scripts to ensure that this is checked as part of telephone contacts | Discussed and agreed approach June 14 | 2014-07-01
Kay | MR7 | C | A card to be sent on the anniversary of every tenancy to gather opinions around tenancy issues and support to stay in their home ( with a prize draw) | This could be costly and may yield a low return around surveys. Explore alternative approaches and how much it would cost to administer. Would be resource intensive if not automatically generated. Following the implementation of the new ICT system - this will be automated | Neighbourhood Managers across Thirteen | Carry out evaluation of this initiative | Discussion and agreed approach by July 2014 | New ICT system will be in place Summer 2015
Kay | MR8 | C | Both landlords to offer a 2-3 year customer contact visit where their tenancy is discussed. This will enable every customer feel valued, build trust and enable any signs of vulnerability or tenancy failure to emerge. | This would be resource intensive and all options of "checking in" with customers could be explored rather than a traditional style visit? Risk based visit approach re-directing resources where most needed maybe more pro-active and cost effective option. | Neighbourhood Managers across Thirteen | Carry out evaluation of this initiative | Discussion and agreed approach by July 2014 | 2014-10-01
Kay | 3.18 | DI | Information and advice on how to manage your tenancy (via the TH and HH websites) should be displayed prominently on the screen in the new kiosks to attract attention of customers | a) We can include more information re: sustaining tenancy on landlord websites and make the link through to the Tandem website more prominent. Tandem website will be updated by end of Aug 2014 b) Display prominently links to Tenancy Mattersd and Money Matters on the kiosks | Lisa Fearn |  |  | 2014-10-01
Kay | 3.18 | DI | Some videos have been developed on money advice and customer involvement projects for example. They are not prominent on our websites and not available on Tristar TV. These should be promoted for customers on the homes page | Agreed re website. Future of Digi TV to be made within the next 12 months however it is a text only service and videos cannot be displayed on the Digi TV service | Kay Glew | Review digi TV in a Tristar context following cost/benefit analysis. If system remains assess ability to see videos through the system | Discussion and agreed approach by July 2014 | Videos in more prominent place on the website by Sept 14. Digi TV by March 15
Kay | MR24 | DI | Posters and adverts to let everyone know that the landlords can help you “get on line” and help you with employment. These should be displayed in as many places as possible, for example: Tristar TV, community centres, libraries, communal areas in flats, GP surgeries and shops | Agreed | Lisa Fearn | To agree publicity approach |  | 2014-08-01
Kay | MR25 | DI | The videos made to give information on tenancy sustainment should be linked from the landlord home page and more information on your own tenancy should be accessed from the website. | Agreed | Lisa Fearn/NMs | To agree approach to implementation |  | 2014-08-01
Kay | 3.29 | DI | Research and draw best practice from the Bromford and Cestria websites as recommended in the report | Agreed | Lisa Fearn/NMs | To agree approach to implementation |  | 2014-08-01
Kay | MR26 | DI | The user-ability of the website needs to be bigger and bolder and important messages for customers should be agreed with customers. In particular, the tenancy sustainment offer and information on the Bromford and Cestria websites are a good benchmark. | Agreed | Lisa Fearn/NMs | To agree approach to implementation | Updated by August 2014 | 2014-08-01
Kay | 3.29 | DI | On the TH website, the section on tenancy support is in the “find a home” area but should be moved to the “customer area” | Agreed | Neighbourhood managers | To agree approach to implementation |  | 2014-08-01
Kay | 3.2 | E | Advice to be given to existing customers paying by key meter with options to see if Thirteen can negotiate with the Credit unions for low- cost loans for key meter change-overs. | Advice can be offered to customers with prepayment meters (Tadea can do this for us at a cost of £33 per home visit if a budget is available). Some energy providers (e.g. Ebico) charge the same rate for fuel regardless of payment method, so changeover may not be necessary (or desired) by customer. Different suppliers have different approaches to key meter changeover, particularly if the customer is in debt, and some requests are refused. Credit union could be an option but need to factor in the interest costs re: loan when weighing up benefits however there is potential that the furniture scheme could be used to fund this initiative via a low cost loan. | Lisa Fearn | a) Agree to produce posters to raise awareness of ability to change key meters now b) Investigate low cost loans and other opportuinities for customers to change from key meters | b) Oct 14 | a) Sept 14 for posters b) March 2015
Kay | 3.23 | E | TH has a contract for collection of water rates. Customers have no choice in this and the water charges are not based on usage. Customers to be advised how to opt out of this. | There is a process currently in place for customers to opt out if this makes financial sense for them. Several customers have already opted out of the scheme. Process to be made clear to staff if customers request a water meter. Review communication approach to informing customers of their option. | Maggie Gibson/Ummar Hanif (NM;s) and Lisa Fearn | Agree approach and implementation see point MR 33 |  | 2014-10-01
Kay | MR33 | E | TH customers should be informed how they can opt out of the water contract | This is available and has been undertaken by several customers although not widely published. Agree that customers could be informed of how this is possible in conjunction with NWB and this to be delivered thorugh a poster campaign in conjunction with advice on how to switch from key meters | Adele McLaren | Discussion with NWB and agreed approach to removal of this element of charge as per previous cases. We appreciate that a number of customers are considering warer meters to help monitor and control consumption/ charges . |  | 2014-08-01
Kay | 3.19 | Em | Customers to have access to a landlord fund to pay travel expenses, bus fares and lunch when they have training, work experience or work, so that they can afford to stay in their home. This could be paid for from the hardship fund for up to 4 weeks’ duration. | We would always look at work programme providers, JCP or other funders first before paying these costs for customers. We are looking at a range of incentives through our pilot Start NOW employability programme which will evaluate the benefits of various incentive approaches and which works best. The programme will be undertaken in the next 6 months and an agreed approach will then follow. Costs have already been paid though for some customers I..e bike bought for a customer to access work as this was their barrier to work (bought via frade) | Lisa Fearn | Evaluate the START now incentive programme prior to full implementation. | Evaluate incentive scheme in place via pilot programme by Dec 2014 prior to roll out. | 2015-03-01
Kay | 3.19 | Em | Consider apprenticeships for people over 25 targeted at customers who are subject to the bedroom tax. This could be further incentivised by paying the bedroom tax for those who go onto apprenticeship or training programme. | Those customers who have a high % of bedroom tax to income have access to the fund and the bedroom tax is paid in part for customers who look to seek employment opportunities. We are reviewing our apprentice programme in a new group context. We will also be reviewing the LDHF in a group context and will consider this recommendation as part of that review | Lisa Fearn/Kay Glew/Stewart Tagg | Review apprenticeship programme along with Alison Joynes and review LDHF with Boards taking into consideration the recommendation around employability. | Agree an approach by December 2014 | 2015-03-01
Kay | 3.1 | F | The recent advert in the Thirteen magazine for the new furniture service at Tristar is not on Tees Credit Union website | Tees Credit Union are renewing their website and all products will be updated following its launch | Kay Glew | Agree approach following launch of Tees Credit Union website |  | 2014-09-01
Kay | MR18 | F | A conversation should be had with the customer when the home is viewed to enable the new customer to access a small loan to own the goods/services that they need, paid back as an extra charge on their rent until the loan is paid off | Agree that this is a priority. Currently TH has a £50K loan scheme for new and existing customers to access low cost furniture via low cost loans. Further promotion is required. Hartlepool also have a scheme available which HH customers can access. Financial inclusion and empty property teams will share information so that the customer is given the relevant information on viewing. Project plan to clarify access to Moneywise, Tandem and Tees Credit union | Julia Kett/Lisa Fearn | Further discussion required as part of service review on empty properties | Project outcomes to be agreed by August 2014 | 2014-10-01 | JK and LF met 30.5.14. The financial inclusion team will share info on credit unions and the empty property teams on second-hand furniture provision. JK will update LF on outcome of service review on empty properties. Funding will need to be identified to facilitate these type of loans for credit union members.
Kay | MR5 | F | Investigate access to recycled furniture or low cost furniture for new and existing customers | Need to explore whether recycled furniture is desired by customers. Need to promote alternative options better i.e. freecycle, Frade etc. | Lisa Fearn | Promote options further and also explore need around recycled items | Discussion and agreed approach by July 2014 | 2014-10-01
Kay | 3.17 | MA | TH doesn’t have a Consumer Credit Licence which limits the type and level of support they can offer individual customers. Debt advice staff can no longer write a letter to enable write off of debts or make repayment plans, CSP would like to renew this licence | TH and HH now have a consumer credit licence under Thirteen but doesn't cover debt. Agreed needs to be extended to cover this area | Lisa Fearn | Establish financial costs and implications of debt licence | 2014-09-01 | 2015-03-01
Kay | 3.17 | MA | GP surgery waiting rooms could be used to promote Money Advice services, would like this and other similar options to be explored | Agreed, but extend to dentists, libraries and the wider community | Lisa Fearn |  |  | 2014-09-01
Kay | 3.17 | MA | Regarding bank account advice, TH/HH advise tenants to stick to Credit Unions and high street banks. There should be formal advice from HH and TH to go to other specific trusted and regulated institutions for a bank account | As landlords we are unable to advise customers due to FSA rules around which accounts are best suited for individual customers, We are allowed to make customers aware of all the options which is the approach taken. | Lisa Fearn | To be prominent on the Tandem and Thirteen/landlords' websites |  | 2014-10-01
Kay | 3.17 | MA | Financial advice is only offered when people are in arrears or at sign up, or maybe through fun days or other events. Facebook and the website should advertise personal our services more | We have utilised face book already to promote money advice services and did this to good effect in the last few months. Agreed that this is something we would want to continue to do. | Adele McLaren | Agree implementation programme in new group wide context and promote again on the website |  | 2014-12-01
Kay | 3.12 | N | In Prior and Melsonby Courts, the issue of reputation and fear of ASB related to drug use was cited as the reason for low demand and tenants leaving the area. A more targeted ASB programme might be necessary in this area. | This is more perception around the blocks, although close working between neighbourhoods and ASB specialist team is important in tackling issues early and pro-actively. | Umar Hannif/ Gilly Marshall | Incorporate the reality versus perception in the new Neighbourhood Plans, and use the local newsletters to promote a positive image of the neighbourhoods | 2014-08-01 | 2015-02-01
Kay | 3.12 | N | Transport is a factor for customers wanting to move out of our estates, bus services are being cut which affects access to work and medical facilities. Landlords to have a conversation with bus companies about the impact these transport cuts are having on our estates | Ongoing discussions have taken place in areas such as the Clarences which is most affected by transport issues. Health needs impact assessment is being carried out in such areas following a meeting with Public Health to address issues around people not having access to health provision through not being able to afford to travel. Meeting to be arranged with transport agencies to improve access to services. A Wider assessment will be carried out to identify which other areas may be affected | Ummar Hanif | To work with LA around discussions with bus services and utilise this knowledge to benefit other areas? | 2014-08-01 | 2015-02-01
Kay | 3.12 | N | Patch managers do not manage rent arrears but as they are the people who are most seen on our estates, they should be trained to give basic advice and support on money advice, DHF and tenancy support | Agreed and within new job profiles | Neighbourhood Managers/Lisa Fearn | To reaffirm following recruitment process | Training programme to be agreed by October 2014 following recruitment | 2015-04-01
Kay | 3.3 | NT | Updated information on the webpages on who the Patch Managers are as these change quite regularly. All relevant customers to be informed when their Patch Manager changes | Agreed but to be completed following recruitment to new roles | Neighbourhood Managers |  |  | 2014-09-01
Kay | 3.6 | NT | Patch managers should flag up to the income recovery team if a new tenant is going to go into arrears, including the time it takes on average when the HB payment should be made. This would remove the need to send letters and cause concern for the tenant | Agreed and within new job profiles | Neighbourhood Managers | To be implemented following implementation to new roles |  | 2014-09-01
Kay | 3.6 | NT | Patch managers to be more thorough at the 4 week visit on advice such as benefits the tenant might be entitled to, whether the tenant was managing with heating costs, access to the handyperson service and reporting repairs or ASB | Agreed and new approach required to first 12 months of tenancy. Would suggest a visit in first week of tenancy and then more regularly built on established relationships. This has also been agreed through the job descriptions, the tenancy sign up will be carried out by the Contracts Team and the rest of the paperwork to be completed by the Patch Manager when the tenant moves in. | Neighbourhood Managers | NMs to agree a timetable of visits/purpose of visits etc. |  | 2014-10-01
Kay | MR4 | NT | A 6 weeks and 6 month visit should take place to enable the patch manager to check that the new customer is coping in their new home, reminding them of the contact details of the patch manager. This to be provided across Group | The timescales require reviewing and 6 weeks check may not be soon enough and additional checks would be beneficial in excess of the two indicated in order to build customer relationships and ensure new tenancies are success.JCs note - report suggests a visit within 2 days as well as 6 week and 6 month visits. This will be bespoke and may be sooner for some especially where it was identified that the tenants may have support needs or vulnerabilities. | Neighbourhood Managers across Thirteen | NMs to agree a timetable of visits/purpose of visits etc. |  | 2014-10-01
Kay | MR1 | PT | An affordability check to be compulsory for all new social housing tenants, to save disappointment of not being able to afford the tenancy at the sign up stage. | Customers need to make informed choices around affordability and is discussed at offer stage. Choice Based lettings is a sub-regional policy and would require sub-regional consultation and support to have this as compulsory. We want to build resilience and allow customers to make their own informed choices. Would recommend affordability check is offered to all new tenants at the pre-offer stage. Enforcing affordability check may impact on our ability to let homes by adding further checks prior to letting. | Lisa Fearn | Discuss with colleagues across group around Thirteen approach to offering affordability checks to all customers at any stage of lettings process, but pro-actively at offer visit / pre-offer stage. | 2014-08-01 | 2015-02-01
Kay | MR2 | PT | A better pre-tenancy assessment is needed. All customers who are offered accommodation for their first rented social home should complete a 2 days course explaining how much it costs to manage a tenancy and how to sustain their tenancy. This might also be targeted at customers who are vulnerable and moving home. | Would agree that further consideration of pre-tenancy assessment/training is required. However, in the current environment, with difficulty letting homes, adding an additional pre-tenancy step would significantly impact on our ability to let homes. Enforcing a 2 day course would be difficult (and not suitable for all e.g.. people in employment or those who are confident with money) but could be used as a way of providing a reference for customers who are struggling to receive a reference as part of the vettings process. The course could also be provided to existing customers? Customers learn in different ways and 121 support during the first few weeks of tenancy maybe more beneficial? | Lisa Fearn | Discuss with colleagues across group around Thirteen approach and in consultation with customers around a proposed pre-tenancy/ new tenancy course or alternatively we are proposing to introduce joint/multi sign ups sessions which would include financial assessment. Also to discuss 121 support during first 12 months of tenancy. | 2014-08-01 | 2015-02-01
Kay | MR23 | ST | An early morning and evening appointment system (like WVAC) to be implemented across all services and all landlords and performance managed to show how well each of the landlords are performing | Appointments are available to meet customers needs and adapted based on customers circumstances. No recognised need currently established and contact team is very quiet 8- 9 and 6-8p.m. Further review is required. | Adele McLaren | Promote on the website access to Tandem including out of hours appointments | Promotion - July 2014 | 2014-10-01
Kay | 3.27 | ST | The positive satisfaction results from the new Tenancy Support Team should be publicised to show off what support is available and the positive outcomes the service can deliver. | The new service will be provided within the Neighbourhood teams by the Neighbourhood officers. As the service will not be a separate team there results maybe confusing. | Kay Glew | Agreed not to deliver this action as results will be confusing |  | Undeliverable
Kay | 3.28 | ST | Feedback the findings from the Scrutiny staff survey and the Scrutiny report to staff groups | Agreed | Kay Glew | To be feedback around approach and implementation plan |  | 2014-09-01
Kay | MR27 | WR | Specific section on each landlord’s website called “Welfare reform” which gives up-to-date, comprehensive and consistent advice to customers, including what help is offered to move and the advice that is available. This should be placed on the home page. | Agreed | Lisa Fearn/Rob Thompson | To agree approach to implementation | Updated by August 2014 | 2014-10-01
Kay | 3.21 | E | Provide some financial support to customers who have their properties thermally imaged, to pay a small amount towards their bills for allowing the landlord to do this | Links to hardship fund, need to establish viability and method of payment | Kay Glew | Subject to Board |  | 2014-10-01
Kay | MR31 | E | All landlords across Group to set up a fund for the customers to change over form key meters | Funds to be considered as part of hardship and credit union developments | Lisa Fearn | Discussion with customers required around establishing need for services | Updated by Oct 14 | 2014-12-01
Kay | MR35 | E | Basic training on energy advice, support to stay, money and benefit advice to be given to all customer facing staff. | This would be resource intensive for all customer facing staff and better for trades to refer customers to the contact team to provide best possible advice. Training to be concentrated on neighbourhood teams. All front facing staff will also be aware of which department to refer into or to contact for advice. | Neighbourhood managers across thirteen | Agree training programme following recruitment into new roles. | Establish training needs for new neighbourhood teams | 2014-10-01
Kay | MR22 | MA | Financial advice should be promoted for all customers and not just to those in arrears. Customers may be paying their rent and getting into debt with other bills | Agreed and is promoted to all customers - i.e. website, telephone messages, face to face discussions etc. Credits on accounts to be regularly reviewed to ensure that any credits can be utilised to pay off other debts. | Lisa Fearn/Rob Thompson | To agree further promotion opportunities/group wide approach to managing credits on account (raised in main body of the report) | Discuss and agree approach by July 2014 | 2014-10-01
Kay | MR20 | WR | Landlords to be clear on council and landlord access to DHP and ensure access has been achieved to both of these. All customers receiving DHP should have the end date/renewal date and be informed as soon as possible of any extension to DHP. This information should be included on the “rent account” viewing area of the websites | Clearer approach to be reviewed via Tandem team. Agree re adding information to rent account viewing areas of the website although no promotion of LDHF on website as Board decision not to promote widely to avoid raising expectations. Targeted approach preferred. | Lisa Fearn / Rob Thompson | Information included in the rent account viewing area of the website as well as generall yin other areas of the website | 2014-07-01 | 2014-12-01
Kay | MR21 | WR | Boards to review their decision to allow landlord DHP to those who have a shortfall of less than 10% and be clear why the arrangement in Prior and Melsonby and Port Clarence is not available for all customers | The LDHF will be reviewed by Board during 2014/15 and was thoroughly reviewed in February 2014 by Board where there was clear understanding based on business decisions around why certain customers in less sustainable areas were given support and other areas did not. LDHF will be reviewed by all Boards across Thirteen during 2014/15 | Kay Glew | Board discussion and officer discussions to take place in order to agree Thirteen's approach to welfare reform | 2014-07-01 | 2014-11-01
Mike | MR29 | E | The new energy consortia OVO should offer their reduced costs energy to valuable existing customers as well as new customers |  | Mike Kay | Subject to business case being approved by the thirteen board. |  | tbc if goes ahead
Mike | 3.2 | E | Every property is surveyed 5 yearly and the database is updated. The CSP would like this survey to include a twin-track fuel poverty assessment. The answer is signposting. Advice to customers as part of this visit. | We currently do an energy rating assessment - SAP and energy rating based on lights, boiler etc. We do that now - extending this - its about disposable income. We need the income of the tenant and then we need to see your energy bills - its confidential - we can ask for them but we cannot demand them - so its hard to acheive this. any individual going inot the home shoudl eb able to recognise things - trades or survyor - shoudl be able to pick up some things like - how warm or cold it is; domestic issues etc. Housing officer shoudl be picking up issues to property and vice versa for signposting. | Geoff Prior | Consider as part of Asset Managament Strategy |  | Tier 4 - Oct and November and then March 2015 | Induction and training required…
Mike | 3.2 | E | Some schemes still have electric storage heaters which are over 30 years old, and suggest a VIP project be carried out on this and whether there is a link with such schemes being hard-to-let | We have a 5 year plan and intend to publish a 2-3 year plan for customers following the approval of the Asset Managament Strategy in Dec 14 and Fuel Poverty strategy in Sept 14. Getting information on systems is an issue using the current IT systme and it will be 12 months for IPACs to include this. | Geoff Prior | Consider as part of Asset Managament Strategy and Fuel Poverty strategy |  | 2014-12-01
Mike | 3.2 | E | Would like the monitoring of the new renewable energy pilots at 6 months and not after 12 months to see if fuel bills are being reduced. This could be done through a VIP project | Accepted norm is 12 months - 4 seasons, will go to Fuel Poverty strategy - Sept 2014. Practical issues - need the structure in place. | Geoff Prior/Steve Boal | Considered as part of Fuel Poverty Strategy |  | 2014-09-01
Mike | 3.2 | E | All staff should be trained on the definition of fuel poverty and swapping of fuel providers when they visit tenants at home, with advice on how to address it | We are developing the idea of collective switching - Boards will decide - the ESCO has the funding - inform tenants about fuel poverty. Business case - 12 motnhs | Mike Kay | Subject to business case for "ESCO" and collective switching being approved by the thirteen board. |  | 2015-06-01
Mike | 3.2 | E | Information on EPCs is not consistently given to customers so they cannot estimate how much they will need to spend on fuel, this should be provided for all properties | EPC ratings are provided at the letting stage for new tenants | Geoff Prior/Brian Robinson | BR to advise if this is practical/possible for existing tenants also |  | 2014-09-01
Mike | MR32 | E | All landlords across the Group to have a strategy for promoting energy switching and door-step advice to make best use of energy in every customers home | This is part of the ESCO project and will be considered by Boards in Sept 14. Recruit, train and develop "Community Energy Champions" to take forward Energy advice in their communities | Mike Kay | Subject to business case being approved by the thirteen board. | 2014-09-01 | 2014-12-01
Mike | 3.21 | E | Develop a programme to carry out thermal imaging across all homes with more staff trained, and targeted first at those properties we know are fuel inefficient and at customers who are struggling financially. Consider investment in more units to enable wider use | Impractical to do all homes currently it is targeted properties. We could make more use of it and would like to do so. Need to consider what is the trigger for using it more widely and we shoudl develop a proticol or prodecude on why when and how (and what happens afterwards) | Brian Robinson | Protocol and procedures agreed and implemented | 2014-11-01 | 2015-01-01
Mike | 3.21 | E | Customers do not realise that condensation is caused by not enough ventilation so this should be promoted more to all customers | Agreed will revisit this and look at the leaflet produced by Tristar Homes with a view to group wide circulation for those homes affected | Brian Robinson | Leaflet produced and information placed on the websites |  | 2014-12-01
Mike | 3.23 | E | Thirteen Group to consider fitting water meters as a useful addition to the investment programme. | Look to introduce a policy for switching to water meters as part of the investment programme. HH have a positive approach but TH not so good | Nik Turner | Policy introduced and part of Asset Management Strategy |  | 2014-12-01
Mike | 3.22 | I | Offer of greater flexibility in hours of service for repairs and investment to accommodate working families | Being negotiated with the unions - part of the revised T&Cs across Thirteen - craftworkers agreement -hours of operation and core and OOH - more flexibility | Mark Robson/Nik Turner | Under negotiation and a groups of people are doing this. |  | 2014-11-01
Mike | 3.22 | I | Consider a multi-layered targeted programme linked to high turnover areas or a sustainability model to ensure that areas most at risk of termination have that investment first. | AMS is influenced by hard to let - a void group is looking at the empties and why they are unpopular | Geoff Prior | Clarification on investment for hard to let properties |  | 2014-12-01
Mike | 3.22 | I | Staff told us that they do not yet have the expertise to maintain the new renewable technologies. Need to ensure a training programme is put in place for trades for the future when the supplier guarantees run out | Accept staff need to be trained -to be considered as part of the Fuel Poverty startegy | Mark Robson | Training programme in place | 2014-09-01 | 2015-01-01
Mike | MR17 | I | Customers to be involved in the investment programme priorities and for landlords to be less reliant on the database | Customer consultation as part of a task and finish group when AMS strategy is approved | Geoff Prior/Nik Turner | Task and finish group in place | 2014-11-01 | 2014-12-01
Mike | MR28 | I | Customers should be informed when investment and improvement works are to be undertaken in order to prevent people terminating their tenancies prematurely | We have a 5 year plan and intend to publish a 2-3 year plan for customers following the approval of the Asset Managament Strategy in Dec 14 and Fuel Poverty strategy in Sept 14. | Geoff Prior | Consider as part of Asset Managament Strategy and Fuel Poverty strategy |  | 2014-12-01
Mike | 3.22 | NT | Following the fitting of new heating systems, staff to revisit homes after 6 months to check customers’ understanding of the new technology. | Agree as a positive suggestion for new build and for those getting new heating systems Need to adopt a flexible approach for renewable technologies TLOs to return after 6 weeks and 6 months for more traditional gas central heating systems | Nik Turner | Develop approach with TLOs |  | 2014-11-01
Mike | 3.3 | NT | Energy advice leaflets given to all new tenants across group - new investment | This will be built into the new tenant visits where the sign up process will be completed with the tenant. | Nik Turner/ Neighbourhood Managers? | Produce leaflets for use across the group at sign up |  | 2014-11-01
Stewart | 3.13 | DI | Hartlepool tenants assume that Tristar tenants have a better deal as they have rent free weeks. This should be explained through media channels that the rent is simply charged over fewer weeks and that the rent is not free | Agreed. Unaware this was a perceived issue and all communication to Tristar customers should state non payment weeks.Agr eed to share in newsletter and website | Rob Thompson | Article in newsletter and info on website |  | 2014-10-01
Stewart | 3.17 | MA | Rent statements are only sent to those in arrears, so those tenants in credit are not receiving money advice literature. Credit on rent accounts is not informed to the tenants who may be able to use this to clear other debts. This needs to be addressed. | See point MR22 re credits. A review of rent statements indicated the financial savings to not sending out rent statements to customers who have clear rent accounts. Agree to send out once a year to all customers in credit including any accompanying literature on financial advice | Lisa Fearn/ Rob Thompson | Agree approach and implementation programme | Discuss and agree approach by July 2014 | 2015-03-01
Stewart | MR9 | N | All local neighbourhoods should have access to local funding such as the ROAP funding at TH, to enable customers in community groups to improve their area and make the neighbourhoods a better place to live | This is something that would be discussed as part of the Customer involvement framework review. ROAP TH funding is in place as part of the "offer document" at transfer. | Stewart Tagg | Review via Customer involvement framework approach | Discussion and agreed approach by September 2014 | 2014-12-01
Stewart | MR10 | ST | Thirteen to explore some of the ideas in tenant reward schemes nationally which might enable greater tenancy sustainment | Would be useful to discuss this with customers/research and insight to be gained to enable further discussion | Paul Noddings | Review approach following insight and business case established to enable evaluation of this option. | Discussion and agreed approach by September 2014 | 2015-03-01
Stewart | MR19 | ST | A number of new strategies for inclusion, tenancy support, affordable warmth and income management did not have accompanying action plans. They were not promoted across both landlords. Customers would like to be involved in shaping of those action plans and monitoring the delivery of new services | All strategic documents in a group context will have an action plan, follow a consistent approach and will be monitored and reviewed via business development team. | Eric Summers/Stewart Tagg | Discussion to take place around the role that customers can play in the review of strategic action plans. | Approach agreed corporately | 2014-06-01
Stewart | MR30 | ST | Rent Policy allows the landlords to charge above or below the recommended rent for that home. Flexibility to be considered where storage heaters are fitted and where rents in our homes are higher than the local rents in the private sector | Not appropriate to use the + or- 5% tolerances, need to priorotise the replacement heating systems | Stewart Tagg |  | Agreed not to deliver | Undeliverable
Stewart | 3.16 | WR | There has been no designation of 3 bed homes to 2 bed homes. Would like TH/HH to look at a minimum size for acceptance that an upstairs room is a bedroom | Current guidelines from the DWP consider a room is a bedroom as long as a bed will fit into it. Some case law is starting to be developed around this area but it is too early and volatile to be relied upon, though we will continue to monitor any developments in this area. Confusion and a lack of correlation between overcrowding legislation and DWP rules and guidelines remains. | Stewart Tagg | Article in newsletter and info on website explaining what a bedroom size is relating bedroom tax rules and policies around allocations and environmental health |  | 2014-10-01
Stewart | 3.16 | WR | The long term plans of TH and HH in terms of DHF are not known. Customers were visited at the onset of bedroom tax and have been informed of the length of time they will receive it. HH and TH should publish their longer terms plans to support customers in the bedroom tax | Government funded DHF/ DHP subsidy is to end at 31st March 2015. The current LDHF was approved to continue for the 2014-15 financial year by both TH and HH Boards. It is to be considered for application across the whole new Group during 2014-15. If it is more widely adopted it is also likely that that both the current scope and qualifying conditions will also be reviewed | Stewart Tagg | Welfare Reform impact to be discussed with Partner Boards | workshops in June / July 2014 .. | Discussed again at Boards in Jan 15
Stewart | 3.16 | WR | The landlords need to be clear that there are 2 routes to supporting them with bedroom tax arrears/payment and promote both.(Council's and landlords) | Govt funded DWP to cease by March 2015. Will promote possible eligibility and work with Councils again this year. Once DWPs applied for TH /HH ts will be considered for LDHF in accordance with scheme guidelines | Stewart Tagg | Article in newsletter and info on website explaining the two routes |  | 2014-10-01
Stewart | 3.16 | WR | The customers in Prior and Melsonby and Port Clarence have all their bedroom tax paid so that they stay. Consideration be given for all customers to have all their bedroom tax paid, weighed against the void costs of £3000 per property | The current LDHF was approved to continue for the 2014-15 financial year by both TH and HH Boards. It is to be considered for application across the whole new Group during 2014-15. If it is more widely adopted it is also likely that that both the current scope and qualifying conditions will also be reviewed | Stewart Tagg | Income Strategy to be produced by Jan 15 which will include cross landlord and local conditions for bedroom tax payments | workshops in June / July 2014 .. | 2015-01-01
Stewart | 3.16 | WR | The numbers of those affected by the bedroom tax goes to Board but the individual data is not known by neighbourhood staff for their patch. Landlords should monitor local take up and set targets for staff to visit homes and update customer data | We are always looking for ways to improve our intelligence regarding the use of customer data and will consider if this approach is both practical and possible within the parameters of our current MIS | Rob Thompson, NMs | Information to be passed to Neighbourhood Managers and used in a targetted appraoch to address support issues |  | 2014-11-01

## area
Lead | No | area | Key Recommendations and areas for improvement | Managers Comment | Officer | Planned Actions and Outcomes | Milestone (date) | Implementation date | Progress since last meeting
Kay | MR6 | C | All contact with customers to include a review and updating of customer profiling information held. | TH and HH have sent out a full survey to customers to update their profile. Contact team should check telephone and profiling information during contacts. Once IPACs and mobile working in place, this will be more possible via neighbourhoods teams. Unlikely to be all staff at all contact but agree it is a priority. | Adele McLaren | To review scripts to ensure that this is checked as part of telephone contacts | Discussed and agreed approach June 14 | 2014-07-01
Kay | MR7 | C | A card to be sent on the anniversary of every tenancy to gather opinions around tenancy issues and support to stay in their home ( with a prize draw) | This could be costly and may yield a low return around surveys. Explore alternative approaches and how much it would cost to administer. Would be resource intensive if not automatically generated. Following the implementation of the new ICT system - this will be automated | Neighbourhood Managers across Thirteen | Carry out evaluation of this initiative | Discussion and agreed approach by July 2014 | New ICT system will be in place Summer 2015
Kay | MR8 | C | Both landlords to offer a 2-3 year customer contact visit where their tenancy is discussed. This will enable every customer feel valued, build trust and enable any signs of vulnerability or tenancy failure to emerge. | This would be resource intensive and all options of "checking in" with customers could be explored rather than a traditional style visit? Risk based visit approach re-directing resources where most needed maybe more pro-active and cost effective option. | Neighbourhood Managers across Thirteen | Carry out evaluation of this initiative | Discussion and agreed approach by July 2014 | 2014-10-01
Andy | 3.18 | DI | The websites allow for anonymous entry of complaints/ASB about the local area. There could be more publicity and promotion of this as it can act as an early warning system for landlords and prevent people leaving due to ASB | Agreed to promote the existing ability for tenants to report ASB anonymously across group | Gilly Marshall | Develop communication plan in a group wide context |  | 2014-08-01
Kay | 3.18 | DI | Information and advice on how to manage your tenancy (via the TH and HH websites) should be displayed prominently on the screen in the new kiosks to attract attention of customers | a) We can include more information re: sustaining tenancy on landlord websites and make the link through to the Tandem website more prominent. Tandem website will be updated by end of Aug 2014 b) Display prominently links to Tenancy Mattersd and Money Matters on the kiosks | Lisa Fearn |  |  | 2014-10-01
Kay | 3.18 | DI | Some videos have been developed on money advice and customer involvement projects for example. They are not prominent on our websites and not available on Tristar TV. These should be promoted for customers on the homes page | Agreed re website. Future of Digi TV to be made within the next 12 months however it is a text only service and videos cannot be displayed on the Digi TV service | Kay Glew | Review digi TV in a Tristar context following cost/benefit analysis. If system remains assess ability to see videos through the system | Discussion and agreed approach by July 2014 | Videos in more prominent place on the website by Sept 14. Digi TV by March 15
Kay | MR24 | DI | Posters and adverts to let everyone know that the landlords can help you “get on line” and help you with employment. These should be displayed in as many places as possible, for example: Tristar TV, community centres, libraries, communal areas in flats, GP surgeries and shops | Agreed | Lisa Fearn | To agree publicity approach |  | 2014-08-01
Kay | MR25 | DI | The videos made to give information on tenancy sustainment should be linked from the landlord home page and more information on your own tenancy should be accessed from the website. | Agreed | Lisa Fearn/NMs | To agree approach to implementation |  | 2014-08-01
Kay | 3.29 | DI | Research and draw best practice from the Bromford and Cestria websites as recommended in the report | Agreed | Lisa Fearn/NMs | To agree approach to implementation |  | 2014-08-01
Kay | MR26 | DI | The user-ability of the website needs to be bigger and bolder and important messages for customers should be agreed with customers. In particular, the tenancy sustainment offer and information on the Bromford and Cestria websites are a good benchmark. | Agreed | Lisa Fearn/NMs | To agree approach to implementation | Updated by August 2014 | 2014-08-01
Kay | 3.29 | DI | On the TH website, the section on tenancy support is in the “find a home” area but should be moved to the “customer area” | Agreed | Neighbourhood managers | To agree approach to implementation |  | 2014-08-01
Stewart | 3.13 | DI | Hartlepool tenants assume that Tristar tenants have a better deal as they have rent free weeks. This should be explained through media channels that the rent is simply charged over fewer weeks and that the rent is not free | Agreed. Unaware this was a perceived issue and all communication to Tristar customers should state non payment weeks.Agr eed to share in newsletter and website | Rob Thompson | Article in newsletter and info on website |  | 2014-10-01
Andy | 3.11 | E | Consultation with customers in Sheltered and Extra care schemes to be carried out about heating levels (and control of this) in the communal areas as many complain it is too hot and they have no control over the temperature | a) consultation within the schemes about heating levels (Andy) b) Implement proposals following the consultation (Mike) c) undertake investment works by March 2015 | Andy Powell, MK | Consultation is straight forward in terms of understanding customer views . Issues will arise with regard to planning into either maintaince or assett management plans | consulatation undertaken by October 2014 | 2015-03-01 | None AP to raise with Jack Dodds re consultation and with assett management
Kay | 3.2 | E | Advice to be given to existing customers paying by key meter with options to see if Thirteen can negotiate with the Credit unions for low- cost loans for key meter change-overs. | Advice can be offered to customers with prepayment meters (Tadea can do this for us at a cost of £33 per home visit if a budget is available). Some energy providers (e.g. Ebico) charge the same rate for fuel regardless of payment method, so changeover may not be necessary (or desired) by customer. Different suppliers have different approaches to key meter changeover, particularly if the customer is in debt, and some requests are refused. Credit union could be an option but need to factor in the interest costs re: loan when weighing up benefits however there is potential that the furniture scheme could be used to fund this initiative via a low cost loan. | Lisa Fearn | a) Agree to produce posters to raise awareness of ability to change key meters now b) Investigate low cost loans and other opportuinities for customers to change from key meters | b) Oct 14 | a) Sept 14 for posters b) March 2015
Kay | 3.23 | E | TH has a contract for collection of water rates. Customers have no choice in this and the water charges are not based on usage. Customers to be advised how to opt out of this. | There is a process currently in place for customers to opt out if this makes financial sense for them. Several customers have already opted out of the scheme. Process to be made clear to staff if customers request a water meter. Review communication approach to informing customers of their option. | Maggie Gibson/Ummar Hanif (NM;s) and Lisa Fearn | Agree approach and implementation see point MR 33 |  | 2014-10-01
Kay | MR33 | E | TH customers should be informed how they can opt out of the water contract | This is available and has been undertaken by several customers although not widely published. Agree that customers could be informed of how this is possible in conjunction with NWB and this to be delivered thorugh a poster campaign in conjunction with advice on how to switch from key meters | Adele McLaren | Discussion with NWB and agreed approach to removal of this element of charge as per previous cases. We appreciate that a number of customers are considering warer meters to help monitor and control consumption/ charges . |  | 2014-08-01
Kay | 3.21 | E | Provide some financial support to customers who have their properties thermally imaged, to pay a small amount towards their bills for allowing the landlord to do this | Links to hardship fund, need to establish viability and method of payment | Kay Glew | Subject to Board |  | 2014-10-01
Kay | MR31 | E | All landlords across Group to set up a fund for the customers to change over form key meters | Funds to be considered as part of hardship and credit union developments | Lisa Fearn | Discussion with customers required around establishing need for services | Updated by Oct 14 | 2014-12-01
Kay | MR35 | E | Basic training on energy advice, support to stay, money and benefit advice to be given to all customer facing staff. | This would be resource intensive for all customer facing staff and better for trades to refer customers to the contact team to provide best possible advice. Training to be concentrated on neighbourhood teams. All front facing staff will also be aware of which department to refer into or to contact for advice. | Neighbourhood managers across thirteen | Agree training programme following recruitment into new roles. | Establish training needs for new neighbourhood teams | 2014-10-01
Mike | MR29 | E | The new energy consortia OVO should offer their reduced costs energy to valuable existing customers as well as new customers |  | Mike Kay | Subject to business case being approved by the thirteen board. |  | tbc if goes ahead
Mike | 3.2 | E | Every property is surveyed 5 yearly and the database is updated. The CSP would like this survey to include a twin-track fuel poverty assessment. The answer is signposting. Advice to customers as part of this visit. | We currently do an energy rating assessment - SAP and energy rating based on lights, boiler etc. We do that now - extending this - its about disposable income. We need the income of the tenant and then we need to see your energy bills - its confidential - we can ask for them but we cannot demand them - so its hard to acheive this. any individual going inot the home shoudl eb able to recognise things - trades or survyor - shoudl be able to pick up some things like - how warm or cold it is; domestic issues etc. Housing officer shoudl be picking up issues to property and vice versa for signposting. | Geoff Prior | Consider as part of Asset Managament Strategy |  | Tier 4 - Oct and November and then March 2015 | Induction and training required…
Mike | 3.2 | E | Some schemes still have electric storage heaters which are over 30 years old, and suggest a VIP project be carried out on this and whether there is a link with such schemes being hard-to-let | We have a 5 year plan and intend to publish a 2-3 year plan for customers following the approval of the Asset Managament Strategy in Dec 14 and Fuel Poverty strategy in Sept 14. Getting information on systems is an issue using the current IT systme and it will be 12 months for IPACs to include this. | Geoff Prior | Consider as part of Asset Managament Strategy and Fuel Poverty strategy |  | 2014-12-01
Mike | 3.2 | E | Would like the monitoring of the new renewable energy pilots at 6 months and not after 12 months to see if fuel bills are being reduced. This could be done through a VIP project | Accepted norm is 12 months - 4 seasons, will go to Fuel Poverty strategy - Sept 2014. Practical issues - need the structure in place. | Geoff Prior/Steve Boal | Considered as part of Fuel Poverty Strategy |  | 2014-09-01
Mike | 3.2 | E | All staff should be trained on the definition of fuel poverty and swapping of fuel providers when they visit tenants at home, with advice on how to address it | We are developing the idea of collective switching - Boards will decide - the ESCO has the funding - inform tenants about fuel poverty. Business case - 12 motnhs | Mike Kay | Subject to business case for "ESCO" and collective switching being approved by the thirteen board. |  | 2015-06-01
Mike | 3.2 | E | Information on EPCs is not consistently given to customers so they cannot estimate how much they will need to spend on fuel, this should be provided for all properties | EPC ratings are provided at the letting stage for new tenants | Geoff Prior/Brian Robinson | BR to advise if this is practical/possible for existing tenants also |  | 2014-09-01
Mike | MR32 | E | All landlords across the Group to have a strategy for promoting energy switching and door-step advice to make best use of energy in every customers home | This is part of the ESCO project and will be considered by Boards in Sept 14. Recruit, train and develop "Community Energy Champions" to take forward Energy advice in their communities | Mike Kay | Subject to business case being approved by the thirteen board. | 2014-09-01 | 2014-12-01
Mike | 3.21 | E | Develop a programme to carry out thermal imaging across all homes with more staff trained, and targeted first at those properties we know are fuel inefficient and at customers who are struggling financially. Consider investment in more units to enable wider use | Impractical to do all homes currently it is targeted properties. We could make more use of it and would like to do so. Need to consider what is the trigger for using it more widely and we shoudl develop a proticol or prodecude on why when and how (and what happens afterwards) | Brian Robinson | Protocol and procedures agreed and implemented | 2014-11-01 | 2015-01-01
Mike | 3.21 | E | Customers do not realise that condensation is caused by not enough ventilation so this should be promoted more to all customers | Agreed will revisit this and look at the leaflet produced by Tristar Homes with a view to group wide circulation for those homes affected | Brian Robinson | Leaflet produced and information placed on the websites |  | 2014-12-01
Mike | 3.23 | E | Thirteen Group to consider fitting water meters as a useful addition to the investment programme. | Look to introduce a policy for switching to water meters as part of the investment programme. HH have a positive approach but TH not so good | Nik Turner | Policy introduced and part of Asset Management Strategy |  | 2014-12-01
Kay | 3.19 | Em | Customers to have access to a landlord fund to pay travel expenses, bus fares and lunch when they have training, work experience or work, so that they can afford to stay in their home. This could be paid for from the hardship fund for up to 4 weeks’ duration. | We would always look at work programme providers, JCP or other funders first before paying these costs for customers. We are looking at a range of incentives through our pilot Start NOW employability programme which will evaluate the benefits of various incentive approaches and which works best. The programme will be undertaken in the next 6 months and an agreed approach will then follow. Costs have already been paid though for some customers I..e bike bought for a customer to access work as this was their barrier to work (bought via frade) | Lisa Fearn | Evaluate the START now incentive programme prior to full implementation. | Evaluate incentive scheme in place via pilot programme by Dec 2014 prior to roll out. | 2015-03-01
Kay | 3.19 | Em | Consider apprenticeships for people over 25 targeted at customers who are subject to the bedroom tax. This could be further incentivised by paying the bedroom tax for those who go onto apprenticeship or training programme. | Those customers who have a high % of bedroom tax to income have access to the fund and the bedroom tax is paid in part for customers who look to seek employment opportunities. We are reviewing our apprentice programme in a new group context. We will also be reviewing the LDHF in a group context and will consider this recommendation as part of that review | Lisa Fearn/Kay Glew/Stewart Tagg | Review apprenticeship programme along with Alison Joynes and review LDHF with Boards taking into consideration the recommendation around employability. | Agree an approach by December 2014 | 2015-03-01
Chris | MR18 | F | TH and HH to have a comprehensive solution to access furniture/white goods for new and existing customers. A conversation should be had with the customer when the home is viewed to enable the new customer to pay more on the rent for white goods, carpets, decoration or whatever a customer needs | On-going discussions are in place around minimum standard and our approach to empty property management. Further work is now required in a group wide context. A charge on the rent is not possible as Thirteen are unable to offer loans currently and would always look at partners i.e. credit unions who have this facility to support these types of requests around white goods/carpets etc. Financial inclusion and empty property teams will share information so that the customer is given the relevant information on viewing. This action links in with access to furniture for existing customers. | Julia Kett/Lisa Fearn | Further discussion required as part of service review on empty properties. Lisa to work through incentives like Smartbuys. Kay to develop the model with Lisa. Chris to work through with patch officers what under menu 3 of the void standard are the incentives that can be offered to applicants | Project outcomes to be agreed by August 2014 | Board will agree the strategy by December 2014 with March 2015 implementation | JK and LF met 30.5.14. The financial inclusion team will share info on credit unions and the empty property teams on second-hand furniture provision. JK will update LF on outcome of service review on empty properties. Funding will need to be identified to facilitate these type of loans for credit union members.
Kay | 3.1 | F | Thirteen group to negotiate with local Housing Benefit departments to assess the feasibility of all new tenants being able to access a furniture package, which is currently only available to those with support needs. | Depending on how the furniture schemes / furniture packs are set up, this can prove to be expensive for customers who move into work and stop claiming housing benefit so this initiative could work against our employability initiatives. Ensure the pre tenancy assesment clarifies who is vulnerable and can therefore access furniture on full HB | Lisa Fearna nd Julie McNaughton | Agree approach | 2014-09-01 | 2014-10-01
Kay | 3.1 | F | The recent advert in the Thirteen magazine for the new furniture service at Tristar is not on Tees Credit Union website | Tees Credit Union are renewing their website and all products will be updated following its launch | Kay Glew | Agree approach following launch of Tees Credit Union website |  | 2014-09-01
Kay | MR18 | F | A conversation should be had with the customer when the home is viewed to enable the new customer to access a small loan to own the goods/services that they need, paid back as an extra charge on their rent until the loan is paid off | Agree that this is a priority. Currently TH has a £50K loan scheme for new and existing customers to access low cost furniture via low cost loans. Further promotion is required. Hartlepool also have a scheme available which HH customers can access. Financial inclusion and empty property teams will share information so that the customer is given the relevant information on viewing. Project plan to clarify access to Moneywise, Tandem and Tees Credit union | Julia Kett/Lisa Fearn | Further discussion required as part of service review on empty properties | Project outcomes to be agreed by August 2014 | 2014-10-01 | JK and LF met 30.5.14. The financial inclusion team will share info on credit unions and the empty property teams on second-hand furniture provision. JK will update LF on outcome of service review on empty properties. Funding will need to be identified to facilitate these type of loans for credit union members.
Kay | MR5 | F | Investigate access to recycled furniture or low cost furniture for new and existing customers | Need to explore whether recycled furniture is desired by customers. Need to promote alternative options better i.e. freecycle, Frade etc. | Lisa Fearn | Promote options further and also explore need around recycled items | Discussion and agreed approach by July 2014 | 2014-10-01
Chris | MR16 | I | Investment works not to be brought forward in a property when a customer leaves as this causes upset on the estate, when the former customer may have moved out due to delays in getting the work done | Links to the Empty homes strategy and void working party, need flexibility and consideration of the local circumstances. Need to work out what the patch officer can do to enable people to stay and how we ensure clear consistent message is communicated to the wider customer base of our approach | Mark Robson/Nik Turner | Agree approach, links to Geoff Prior's work on 3 voids standards and the timescales for this above. |  | Board will agree the strategy by December 2014 with March 2015 implementation
Mike | 3.22 | I | Offer of greater flexibility in hours of service for repairs and investment to accommodate working families | Being negotiated with the unions - part of the revised T&Cs across Thirteen - craftworkers agreement -hours of operation and core and OOH - more flexibility | Mark Robson/Nik Turner | Under negotiation and a groups of people are doing this. |  | 2014-11-01
Mike | 3.22 | I | Consider a multi-layered targeted programme linked to high turnover areas or a sustainability model to ensure that areas most at risk of termination have that investment first. | AMS is influenced by hard to let - a void group is looking at the empties and why they are unpopular | Geoff Prior | Clarification on investment for hard to let properties |  | 2014-12-01
Mike | 3.22 | I | Staff told us that they do not yet have the expertise to maintain the new renewable technologies. Need to ensure a training programme is put in place for trades for the future when the supplier guarantees run out | Accept staff need to be trained -to be considered as part of the Fuel Poverty startegy | Mark Robson | Training programme in place | 2014-09-01 | 2015-01-01
Mike | MR17 | I | Customers to be involved in the investment programme priorities and for landlords to be less reliant on the database | Customer consultation as part of a task and finish group when AMS strategy is approved | Geoff Prior/Nik Turner | Task and finish group in place | 2014-11-01 | 2014-12-01
Mike | MR28 | I | Customers should be informed when investment and improvement works are to be undertaken in order to prevent people terminating their tenancies prematurely | We have a 5 year plan and intend to publish a 2-3 year plan for customers following the approval of the Asset Managament Strategy in Dec 14 and Fuel Poverty strategy in Sept 14. | Geoff Prior | Consider as part of Asset Managament Strategy and Fuel Poverty strategy |  | 2014-12-01
Kay | 3.17 | MA | TH doesn’t have a Consumer Credit Licence which limits the type and level of support they can offer individual customers. Debt advice staff can no longer write a letter to enable write off of debts or make repayment plans, CSP would like to renew this licence | TH and HH now have a consumer credit licence under Thirteen but doesn't cover debt. Agreed needs to be extended to cover this area | Lisa Fearn | Establish financial costs and implications of debt licence | 2014-09-01 | 2015-03-01
Kay | 3.17 | MA | GP surgery waiting rooms could be used to promote Money Advice services, would like this and other similar options to be explored | Agreed, but extend to dentists, libraries and the wider community | Lisa Fearn |  |  | 2014-09-01
Kay | 3.17 | MA | Regarding bank account advice, TH/HH advise tenants to stick to Credit Unions and high street banks. There should be formal advice from HH and TH to go to other specific trusted and regulated institutions for a bank account | As landlords we are unable to advise customers due to FSA rules around which accounts are best suited for individual customers, We are allowed to make customers aware of all the options which is the approach taken. | Lisa Fearn | To be prominent on the Tandem and Thirteen/landlords' websites |  | 2014-10-01
Kay | 3.17 | MA | Financial advice is only offered when people are in arrears or at sign up, or maybe through fun days or other events. Facebook and the website should advertise personal our services more | We have utilised face book already to promote money advice services and did this to good effect in the last few months. Agreed that this is something we would want to continue to do. | Adele McLaren | Agree implementation programme in new group wide context and promote again on the website |  | 2014-12-01
Kay | MR22 | MA | Financial advice should be promoted for all customers and not just to those in arrears. Customers may be paying their rent and getting into debt with other bills | Agreed and is promoted to all customers - i.e. website, telephone messages, face to face discussions etc. Credits on accounts to be regularly reviewed to ensure that any credits can be utilised to pay off other debts. | Lisa Fearn/Rob Thompson | To agree further promotion opportunities/group wide approach to managing credits on account (raised in main body of the report) | Discuss and agree approach by July 2014 | 2014-10-01
Stewart | 3.17 | MA | Rent statements are only sent to those in arrears, so those tenants in credit are not receiving money advice literature. Credit on rent accounts is not informed to the tenants who may be able to use this to clear other debts. This needs to be addressed. | See point MR22 re credits. A review of rent statements indicated the financial savings to not sending out rent statements to customers who have clear rent accounts. Agree to send out once a year to all customers in credit including any accompanying literature on financial advice | Lisa Fearn/ Rob Thompson | Agree approach and implementation programme | Discuss and agree approach by July 2014 | 2015-03-01
Chris | 3.14 | MEXT | Customer on the transfer list who have an arrears agreement should be able to be given the opportunity to catch up on a payment that they missed by being a sent a reminder, in order for them to stay on the list and not go back to week one | Flexibility and office discretion is required which reflects tenants circumstances but which still aligns to the need for customers to show a long term commitment to rent repayments prior to accessing the register. | Julie McNaughton | Agree training following recruitment into new roles to ensure consistency of approach. |  | 2014-10-01
Chris | 3.5 | MEXT | Transfer customers should be given at least 1 full working day to make arrangements prior to moving. If keys are given out after Thursday for transfer customers, the customer should not have to pay the week’s rent for their old home | This will need reviewing as part of the Empty Property review. Many team involved - had 2 meeting so far (30th June)from this we need an overarching strategy on where we are going. As part of this remit we will have task and finish groups with customers in August 2014 interested in all elements of tenancy management, lettings, finance etc. and we may be able to pilot some of the ideas before Dec 14 | Chris Joynes | Establish project team to review empty property management and timetable. Staff group already established. | First meeting to take place by July 2014 which will establish project plan | Board will agree the strategy by December 2014 with March 2015 implementation
Kay | MR11 | MEXT | Customers who apply for an exchange or a transfer should do so through the Patch Manager who can discuss what might enable the customer to stay. Immediate visits should be carried out to see if the landlords can take action before they terminate their tenancy | Agreed that these visits will take place by neighbourhood teams although timescales around visits will need to be agreed. This will form part of the inspection visit to all tenants following a transfer application form or mutual exchange application being registered. This is to prevent losing tenants who may also leave the company through other landlords. | Neighbourhood Managers across Thirteen | NM/s to agree an approach to support customers who identify that they want to transfer/mutual exchange/terminate their tenancy | Discussion and agreed approach by July 2014 | 2014-08-01
Kay | 3.14 | MEXT | Staff felt mutual exchanges were costly due to the checks that needed to be done, so there was no benefit to the landlord to encourage it. Some staff do not know they work. Mutual exchanges should be supported, and staff should be trained to promote it | Agreed and this is a low cost solution. | Kay Glew/Andy Powell in TH and HH context | Pro-active discussion with Neighbourhoods teams and agree training programme following recruitment into new roles. |  | 2014-10-01
Kay | 3.14 | MEXT | Customers said they got no support to achieve a mutual exchange and they would rather see a member of staff employed to match the mutual exchange applicants, rather than waste money paying out on DHP. | The DHP scheme has been well supported by customers following a review of the scheme after 6 months. Neighbourhood officers will be responsible in a group context for mutual exchange process supporting customers with matching opportunities. It is felt that localised officers are better placed than having one dedicated officer. This has been passed to Neighbourhoods by The Contracts Team to deal with from start to finish | Neighbourhood Managers | Discuss approach following recruitment to the neighbourhood teams and ensure appropriate training is in place | Establish process following recruitment to teams- Sept - 2014 | 2014-10-01
Kay | 3.29 | MEXT | Vela’s most recent Mutual Exchange Policy to be placed on the websites of TH and HH | Agreed | Neighbourhood Managers | Add to website |  | 2014-08-01
Kay | MR12 | MEXT | Customers who need to move should be able to get support from a specialist person who can explore 2 and 3-way mutual exchanges and enable the move to release at least one of the customers from bedroom tax costs | This role would fit within the neighbourhood service. We would always want to pro-actively support and facilitate mutual exchanges as a low cost solution to meet customers rehousing needs | Neighbourhood managers | DF with colleagues to establish an approach in a thirteen context. | Discussion and agreed approach by July 2014 | 2014-10-01
Andy | 3.13 | N | Customers need to feel empowered to collectively support landlords in enforcement action against ASB, this would make a useful project to investigate for the VIPs. | Scrutiny group to meet Gilly Marshall to explore options and possible VIP project | Gilly Marshall |  | 2014-07-01 | 2014-12-01
Andy | 3.12 | N | HH patch sizes to be equalised with the TH patch sizes, or be able to refer complex cases to a group-wide Tenancy Support team | All patches will be reviewed as part of the neighbourhoods review.We are also exploring how we can work with Thirteen's Care and Support team to acces support services. | Andy Powell | AP to review the methodology for fixing allocations between Neighbourhood teams | 2014-07-01 | 2014-07-01
Kay | 3.12 | N | When estates are improved and demand goes up, HH and TH should increase positive publicity to remove the poor reputation of estates and make people proud of where they live | Agreed that a pro-active approach is needed | Kay Glew | Agree approach and implementation programme | 2014-08-01 | 2014-10-01
Kay | 3.12 | N | In Prior and Melsonby Courts, the issue of reputation and fear of ASB related to drug use was cited as the reason for low demand and tenants leaving the area. A more targeted ASB programme might be necessary in this area. | This is more perception around the blocks, although close working between neighbourhoods and ASB specialist team is important in tackling issues early and pro-actively. | Umar Hannif/ Gilly Marshall | Incorporate the reality versus perception in the new Neighbourhood Plans, and use the local newsletters to promote a positive image of the neighbourhoods | 2014-08-01 | 2015-02-01
Kay | 3.12 | N | Transport is a factor for customers wanting to move out of our estates, bus services are being cut which affects access to work and medical facilities. Landlords to have a conversation with bus companies about the impact these transport cuts are having on our estates | Ongoing discussions have taken place in areas such as the Clarences which is most affected by transport issues. Health needs impact assessment is being carried out in such areas following a meeting with Public Health to address issues around people not having access to health provision through not being able to afford to travel. Meeting to be arranged with transport agencies to improve access to services. A Wider assessment will be carried out to identify which other areas may be affected | Ummar Hanif | To work with LA around discussions with bus services and utilise this knowledge to benefit other areas? | 2014-08-01 | 2015-02-01
Kay | 3.12 | N | Patch managers do not manage rent arrears but as they are the people who are most seen on our estates, they should be trained to give basic advice and support on money advice, DHF and tenancy support | Agreed and within new job profiles | Neighbourhood Managers/Lisa Fearn | To reaffirm following recruitment process | Training programme to be agreed by October 2014 following recruitment | 2015-04-01
Stewart | MR9 | N | All local neighbourhoods should have access to local funding such as the ROAP funding at TH, to enable customers in community groups to improve their area and make the neighbourhoods a better place to live | This is something that would be discussed as part of the Customer involvement framework review. ROAP TH funding is in place as part of the "offer document" at transfer. | Stewart Tagg | Review via Customer involvement framework approach | Discussion and agreed approach by September 2014 | 2014-12-01
Chris | 3.3 | NT | All new tenants be assessed for the Tenancy Support Service (group-wide) - only happens in Tristar. Also customers used to complete a risk of tenancy failure assessment at the bidding stage, this should be re-introduced across both landlords | The Lettings team are aligning processes and highlighting any good practices to include within this work and role across the Thirteen group. The group will explore the previous process as outlined and bring all working practices together. | Julie McNaughton | December 2014 Board - agree the Strategy. March 2015 implementation | 2014-09-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.3 | NT | Decoration standards and allowances should be brought together across group. A handyperson or decorating service should be considered across Group, either as a social enterprise or otherwise | To be reviewed as part of Empty Property Review. An Interim agreemet of 3 standards has been agreed 1 = DHS; 2 = DHS and decoration; 3 = DHS plus enhancements - Geoff Pryor working on a definition - categorisation of each void will be based on Patch manager decision of knowledge of area and lettability issues | Chris Joynes | Project team approach required to agree new approach to managing voids in a thirteen context | Agreed standard and decoration allowance to be in place Dec 14. Some piloting of ideas to Dec 2014. | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.3 | NT | Staff reminded to go through everything in the sign up pack, they give out lots of information but there may not be sufficient focus on money advice. | We are proposing to introduce joint/multi sign up approaches and possibly a pre-sign up which would include financial assessment/awareness session briefings. Current thinking is DVD which is already available but needs "Thirteen" branding. Also developing a unified tenancy agreement. Slight changes in this to go onto DVD | Julie McNaughton | Agree approach in a group wide context | 2014-08-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.9 | NT | The staff should explain to new customers the importance of taking meter readings and immediately informing the utility companies about the tenancy change | This should be standard practice. Note: we have entered into a partnership as part of a wider consortia (Mike Kay lead officer) with OVO Energy (proffered supplier). We are about to embark on a pilot in Middlesbrough where SMART meters will be installed in empty properties and the process will factor in meter readings and switching utilities to the preferred supplier, providing this is what the tenant wants. | Julia Kett/Neighbourhood Managers | This should be in place and reaffirmed following recruitment to new roles. Patch manager will have a converstaion with the incoming and outgoing teant to ensure they take meter readings |  | September 2014 - all teams will be togather and be in the same message
Kay | 3.3 | NT | Updated information on the webpages on who the Patch Managers are as these change quite regularly. All relevant customers to be informed when their Patch Manager changes | Agreed but to be completed following recruitment to new roles | Neighbourhood Managers |  |  | 2014-09-01
Kay | 3.6 | NT | Patch managers should flag up to the income recovery team if a new tenant is going to go into arrears, including the time it takes on average when the HB payment should be made. This would remove the need to send letters and cause concern for the tenant | Agreed and within new job profiles | Neighbourhood Managers | To be implemented following implementation to new roles |  | 2014-09-01
Kay | 3.6 | NT | Patch managers to be more thorough at the 4 week visit on advice such as benefits the tenant might be entitled to, whether the tenant was managing with heating costs, access to the handyperson service and reporting repairs or ASB | Agreed and new approach required to first 12 months of tenancy. Would suggest a visit in first week of tenancy and then more regularly built on established relationships. This has also been agreed through the job descriptions, the tenancy sign up will be carried out by the Contracts Team and the rest of the paperwork to be completed by the Patch Manager when the tenant moves in. | Neighbourhood Managers | NMs to agree a timetable of visits/purpose of visits etc. |  | 2014-10-01
Kay | MR4 | NT | A 6 weeks and 6 month visit should take place to enable the patch manager to check that the new customer is coping in their new home, reminding them of the contact details of the patch manager. This to be provided across Group | The timescales require reviewing and 6 weeks check may not be soon enough and additional checks would be beneficial in excess of the two indicated in order to build customer relationships and ensure new tenancies are success.JCs note - report suggests a visit within 2 days as well as 6 week and 6 month visits. This will be bespoke and may be sooner for some especially where it was identified that the tenants may have support needs or vulnerabilities. | Neighbourhood Managers across Thirteen | NMs to agree a timetable of visits/purpose of visits etc. |  | 2014-10-01
Mike | 3.22 | NT | Following the fitting of new heating systems, staff to revisit homes after 6 months to check customers’ understanding of the new technology. | Agree as a positive suggestion for new build and for those getting new heating systems Need to adopt a flexible approach for renewable technologies TLOs to return after 6 weeks and 6 months for more traditional gas central heating systems | Nik Turner | Develop approach with TLOs |  | 2014-11-01
Mike | 3.3 | NT | Energy advice leaflets given to all new tenants across group - new investment | This will be built into the new tenant visits where the sign up process will be completed with the tenant. | Nik Turner/ Neighbourhood Managers? | Produce leaflets for use across the group at sign up |  | 2014-11-01
Andy | 3.11 | O | Services offered to older and vulnerable customers in HH should be offered to customers from all landlords across Group | Subject to the development of the Older Persons Housing Strategy and local commissioning variations and the views of customers outside Hartlepool | Andy Powell, Paul Noddings | Develop Older Person Housing Strategy | Scope of Strategy to be agreed by July 2014 | 2014-12-01
Andy | 3.11 | O | More promotion of the benefits of moving to sheltered accommodation rather than moving out of a 3 bed housing into a care home, and moving encouraged before the stage when they can no longer be accepted for sheltered accommodation | Marketing and review of the accomodation for older persons to be included within the Older Persons Housing Strategy | Andy Powell |  | Scope of Strategy to be agreed by July 2014 | 2014-12-01
Andy | 3.11 | O | The Customer involvement action plan that was produced in 2013 for Extra care and sheltered accommodation in HH to be implemented | Specific resource for this identified within the CI structure for a CI plan across the group for older people | Andy Powell |  | 2014-09-01 | 2014-12-01
Chris | 3.1 | PT | Some work started in the involvement team to produce some short videos about what it means to have a tenancy however this was not completed. These should be completed and placed on the website | DVDs have been produced for new customers for tenancy induction purposes in some parts of the new Group. We would like to update these where applicable and extend the availability of visual material across all partner landlords. Need to link with the KYM project and develop short videos/DVD for Young People with the new Customer Invovlement Manager | Julie McNaughton and CIM | Task and finish group to be established to agree what videos and timescales. Need to understand what the Young People want to know - speak to colleges and those in later school ages | Will have DVD for September 2014 | 2014-11-01
Kay | MR1 | PT | An affordability check to be compulsory for all new social housing tenants, to save disappointment of not being able to afford the tenancy at the sign up stage. | Customers need to make informed choices around affordability and is discussed at offer stage. Choice Based lettings is a sub-regional policy and would require sub-regional consultation and support to have this as compulsory. We want to build resilience and allow customers to make their own informed choices. Would recommend affordability check is offered to all new tenants at the pre-offer stage. Enforcing affordability check may impact on our ability to let homes by adding further checks prior to letting. | Lisa Fearn | Discuss with colleagues across group around Thirteen approach to offering affordability checks to all customers at any stage of lettings process, but pro-actively at offer visit / pre-offer stage. | 2014-08-01 | 2015-02-01
Kay | MR2 | PT | A better pre-tenancy assessment is needed. All customers who are offered accommodation for their first rented social home should complete a 2 days course explaining how much it costs to manage a tenancy and how to sustain their tenancy. This might also be targeted at customers who are vulnerable and moving home. | Would agree that further consideration of pre-tenancy assessment/training is required. However, in the current environment, with difficulty letting homes, adding an additional pre-tenancy step would significantly impact on our ability to let homes. Enforcing a 2 day course would be difficult (and not suitable for all e.g.. people in employment or those who are confident with money) but could be used as a way of providing a reference for customers who are struggling to receive a reference as part of the vettings process. The course could also be provided to existing customers? Customers learn in different ways and 121 support during the first few weeks of tenancy maybe more beneficial? | Lisa Fearn | Discuss with colleagues across group around Thirteen approach and in consultation with customers around a proposed pre-tenancy/ new tenancy course or alternatively we are proposing to introduce joint/multi sign ups sessions which would include financial assessment. Also to discuss 121 support during first 12 months of tenancy. | 2014-08-01 | 2015-02-01
Kay | MR23 | ST | An early morning and evening appointment system (like WVAC) to be implemented across all services and all landlords and performance managed to show how well each of the landlords are performing | Appointments are available to meet customers needs and adapted based on customers circumstances. No recognised need currently established and contact team is very quiet 8- 9 and 6-8p.m. Further review is required. | Adele McLaren | Promote on the website access to Tandem including out of hours appointments | Promotion - July 2014 | 2014-10-01
Kay | 3.27 | ST | The positive satisfaction results from the new Tenancy Support Team should be publicised to show off what support is available and the positive outcomes the service can deliver. | The new service will be provided within the Neighbourhood teams by the Neighbourhood officers. As the service will not be a separate team there results maybe confusing. | Kay Glew | Agreed not to deliver this action as results will be confusing |  | Undeliverable
Kay | 3.28 | ST | Feedback the findings from the Scrutiny staff survey and the Scrutiny report to staff groups | Agreed | Kay Glew | To be feedback around approach and implementation plan |  | 2014-09-01
Stewart | MR10 | ST | Thirteen to explore some of the ideas in tenant reward schemes nationally which might enable greater tenancy sustainment | Would be useful to discuss this with customers/research and insight to be gained to enable further discussion | Paul Noddings | Review approach following insight and business case established to enable evaluation of this option. | Discussion and agreed approach by September 2014 | 2015-03-01
Stewart | MR19 | ST | A number of new strategies for inclusion, tenancy support, affordable warmth and income management did not have accompanying action plans. They were not promoted across both landlords. Customers would like to be involved in shaping of those action plans and monitoring the delivery of new services | All strategic documents in a group context will have an action plan, follow a consistent approach and will be monitored and reviewed via business development team. | Eric Summers/Stewart Tagg | Discussion to take place around the role that customers can play in the review of strategic action plans. | Approach agreed corporately | 2014-06-01
Stewart | MR30 | ST | Rent Policy allows the landlords to charge above or below the recommended rent for that home. Flexibility to be considered where storage heaters are fitted and where rents in our homes are higher than the local rents in the private sector | Not appropriate to use the + or- 5% tolerances, need to priorotise the replacement heating systems | Stewart Tagg |  | Agreed not to deliver | Undeliverable
Andy | 3.25 | T | Develop customer profiling to link hot spots of tenancy turnover to the sustainment needs and to target tenancy sustainment activity to these hot spots | This layering of information is occuring via the sustainability model | NMs | Request that MA highlight this within the Sustainability Tool | Feedback from MA on achieveability June 14 | 2014-09-01
Chris | 3.25 | T | Ensure both landlords collect the same data on termination reasons and look at ways to incentivise customers to allow termination visits when people are looking to leave. Promote the benefits of security of tenancy and other rights, as a benefit for staying in our homes rather than leaving for the private rented sector | There is some consistency but limited to some extent by ICT issues. This will be resolved via IPACS implementation.Keen to have a tempate which can be interrogated. Terminaton reasons to be agreed by August 2014 and will collect it on an excel spreadsheet until IPACs in place. The procedures for termination visits and access incentives will sit under the policy, as will how we promote the benefits of being a Thirteen tenant | Chris Joynes | Review as part of IPACs implementation. | Agree approach following IPACs contract being awarded - October 2014 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.25 | T | Customers to be involved in any review of the Tenancy Policy under the Thirteen group, be consulted on affordable rents and fixed term tenancies and their impact on people choosing our properties or choosing to leave them | New Tenancy Policy needs to be developed in a Thirteen context and linked to the new strategic TeesValley local authority framework. 14 partner policy areas being joined together. Task and finish groups of tenants to be involved. | Chris Joynes | Policy will undergo a full Equality Needs Impact Assessment | New policy in place Dec 14 | 2014-12-01
Chris | MR14 | T | A customer who says they are leaving should be visited not just for repairs when the tenancy has ended, but immediately as notice is given by the patch manager to see if it is possible to support them to remain in their home. | Agreed. EH & TVH voids Task & Finish Group have agreed a new process i.e. the pre-termination inspection is carried out by the neighbourhood teams instead of the empty property team, as they have the local knowledge in terms of tenancy conduct and any issues that need to be addressed. The pilot is working well and it is anticipated that it will be rolled out Group wide in the next few weeks/months. Links to Support to Stay initiative and Neighbourhood Sustainability Pilots. Patch manager must now speak to everyone who is going to see if they can persuade them to stay | Neighbourhood Managers across Thirteen & Julie McNaughton | Discuss agreed approach | 2014-07-01 | 2014-11-01
Chris | MR15 | V | The minimum void standard should be increased to to compete with the private rented sector and give customers the best possible start in their new home. The homes should always be deep cleaned, so customers can move in with the minimum of effort. When in future the void standard is reviewed, it should incorporate decoration issues and customers to be involved in this review | On-going discussions are in place around minimum standard and our approach to empty property management. Further work is now required in a group wide context. The standard maybe linked to size/location to determine the standard. | Julia Kett | Project team approach required to agree new approach to managing voids in a thirteen context | 2014-07-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | 3.2 | WP | The Welcome pack should be placed on the website and the information could be printed only for those who cannot access the website. Those customers who are dyslexic or struggling to read quickly, should be able to access the information in the Welcome pack through videos placed on our websites | Agree that this information should be available via the website once the welcome pack has been updated this will be progressed. We have developed a DVD that can be played in sections that covers the main information and requirements for their tenancy. The intention is to include this on the websites once it has been branded for all organisations | Julie McNaughton | Update DVD ensure branding is appropriate and make accessible via the website | 2014-09-01 | 2014-10-01
Chris | MR3 | WP | The Welcome packs should be more professional, simplified and some of the papers should be given at offer or viewing stage to ensure customers have a better understanding and information about their tenancy. New tenants should be asked to sign a checklist that they have been given and understood the contents | Agree that paperwork needs to be professional, simplified and consistent. There is a working group looking at the Welcome sign up pack. This will be streamlined to focus on the importance of the contractual agreement. The neighbourhood teams will take the rest of the information to the welcome visit. | Julie McNaughton | Discuss with colleagues across group and customers around Thirteen approach to the sign up process ensuring also that neighbourhood teams visit in the property within first week or two? | Discussion and agreed approach by July 2014 | 2014-10-01
Chris | 3.16 | WR | Flat should be offered to families with children to enable them to downsize, rather than to leave for the private sector | This was introduced within the allocations policy within the last review. This needs to be neighbourhood led as they need to identify suitable flats that would accommodate a family unit without causing any sustainability issues. Need to agree an approach - The neighbourhood team need to confirm suitability at the advertisement stage considering the neighbourhood and suitability. Patch manager must now speak to everyone if they are going to recommend a local lettings polic | Julie McNaughton | Training to be rolled out to the neighbourhood teams to ensure that suitable properties are advertised to allow families to bid. | When Neighbourhood Officers are in place they can influence the local lettings policies | Implementation will follow conversations with customers in the blocks/area from September 2014
Chris | MR13 | WR | The rules for allocations to change to allow those who can upsize and pay for this, to be able to do this. Staff should be trained to understand that the allocations policy allows those who can pay for 3 bed homes to upsize, even if they are under-occupying. | Allocations are via CBL sub regional scheme and customers do have some flexibility to upsize i.e. 1/2 bedroom need for individuals and couples; 2/3 for couple/single with one child etc. although priority goes to customers who have a need for the number of rooms indicated. These discussions do take place with customers. Discussion required around enabling single people to apply for properties much bigger than their needs on an area basis in particular where there is low demand but customers can afford to upsize. | Julie McNaughton | Establish a unified approach in a Thirteen context. We will advertise based on need and if cannot allocate then can offer to others. Needs implementation of the new officers and teams from September to ensure this message goes across all teams | August 2014. | September 2014 - all teams will be togather and be in the same message
Chris | MR34 | WR | VIPs to undertake an investigation into the offer made in the private sector and a separate investigation into those subject to the bedroom tax to be able to talk to them about the support they need. | Julie to work with Jonathan Cannon from CI team on a CSI project to her brief starting July 2014. | Julie McNaughton | CSI project for HH and TH to investigate PRS offer in July/August 2014 | August 2014. | 2014-12-01 | Mystery shopping to be carreid out in July on the Private Rented sector offer by CSI group
Kay | MR27 | WR | Specific section on each landlord’s website called “Welfare reform” which gives up-to-date, comprehensive and consistent advice to customers, including what help is offered to move and the advice that is available. This should be placed on the home page. | Agreed | Lisa Fearn/Rob Thompson | To agree approach to implementation | Updated by August 2014 | 2014-10-01
Kay | MR20 | WR | Landlords to be clear on council and landlord access to DHP and ensure access has been achieved to both of these. All customers receiving DHP should have the end date/renewal date and be informed as soon as possible of any extension to DHP. This information should be included on the “rent account” viewing area of the websites | Clearer approach to be reviewed via Tandem team. Agree re adding information to rent account viewing areas of the website although no promotion of LDHF on website as Board decision not to promote widely to avoid raising expectations. Targeted approach preferred. | Lisa Fearn / Rob Thompson | Information included in the rent account viewing area of the website as well as generall yin other areas of the website | 2014-07-01 | 2014-12-01
Kay | MR21 | WR | Boards to review their decision to allow landlord DHP to those who have a shortfall of less than 10% and be clear why the arrangement in Prior and Melsonby and Port Clarence is not available for all customers | The LDHF will be reviewed by Board during 2014/15 and was thoroughly reviewed in February 2014 by Board where there was clear understanding based on business decisions around why certain customers in less sustainable areas were given support and other areas did not. LDHF will be reviewed by all Boards across Thirteen during 2014/15 | Kay Glew | Board discussion and officer discussions to take place in order to agree Thirteen's approach to welfare reform | 2014-07-01 | 2014-11-01
Stewart | 3.16 | WR | There has been no designation of 3 bed homes to 2 bed homes. Would like TH/HH to look at a minimum size for acceptance that an upstairs room is a bedroom | Current guidelines from the DWP consider a room is a bedroom as long as a bed will fit into it. Some case law is starting to be developed around this area but it is too early and volatile to be relied upon, though we will continue to monitor any developments in this area. Confusion and a lack of correlation between overcrowding legislation and DWP rules and guidelines remains. | Stewart Tagg | Article in newsletter and info on website explaining what a bedroom size is relating bedroom tax rules and policies around allocations and environmental health |  | 2014-10-01
Stewart | 3.16 | WR | The long term plans of TH and HH in terms of DHF are not known. Customers were visited at the onset of bedroom tax and have been informed of the length of time they will receive it. HH and TH should publish their longer terms plans to support customers in the bedroom tax | Government funded DHF/ DHP subsidy is to end at 31st March 2015. The current LDHF was approved to continue for the 2014-15 financial year by both TH and HH Boards. It is to be considered for application across the whole new Group during 2014-15. If it is more widely adopted it is also likely that that both the current scope and qualifying conditions will also be reviewed | Stewart Tagg | Welfare Reform impact to be discussed with Partner Boards | workshops in June / July 2014 .. | Discussed again at Boards in Jan 15
Stewart | 3.16 | WR | The landlords need to be clear that there are 2 routes to supporting them with bedroom tax arrears/payment and promote both.(Council's and landlords) | Govt funded DWP to cease by March 2015. Will promote possible eligibility and work with Councils again this year. Once DWPs applied for TH /HH ts will be considered for LDHF in accordance with scheme guidelines | Stewart Tagg | Article in newsletter and info on website explaining the two routes |  | 2014-10-01
Stewart | 3.16 | WR | The customers in Prior and Melsonby and Port Clarence have all their bedroom tax paid so that they stay. Consideration be given for all customers to have all their bedroom tax paid, weighed against the void costs of £3000 per property | The current LDHF was approved to continue for the 2014-15 financial year by both TH and HH Boards. It is to be considered for application across the whole new Group during 2014-15. If it is more widely adopted it is also likely that that both the current scope and qualifying conditions will also be reviewed | Stewart Tagg | Income Strategy to be produced by Jan 15 which will include cross landlord and local conditions for bedroom tax payments | workshops in June / July 2014 .. | 2015-01-01
Stewart | 3.16 | WR | The numbers of those affected by the bedroom tax goes to Board but the individual data is not known by neighbourhood staff for their patch. Landlords should monitor local take up and set targets for staff to visit homes and update customer data | We are always looking for ways to improve our intelligence regarding the use of customer data and will consider if this approach is both practical and possible within the parameters of our current MIS | Rob Thompson, NMs | Information to be passed to Neighbourhood Managers and used in a targetted appraoch to address support issues |  | 2014-11-01

## Main recs only
Lead | No | area | Key Recommendations and areas for improvement | Managers Comment | Officer | Planned Actions and Outcomes | Milestone (date) | Implementation date | Progress since last meeting
Kay | MR1 | PT | An affordability check to be compulsory for all new social housing tenants, to save disappointment of not being able to afford the tenancy at the sign up stage. | Customers need to make informed choices around affordability and is discussed at offer stage. Choice Based lettings is a sub-regional policy and would require sub-regional consultation and support to have this as compulsory. We want to build resilience and allow customers to make their own informed choices. Would recommend affordability check is offered to all new tenants at the pre-offer stage. Enforcing affordability check may impact on our ability to let homes by adding further checks prior to letting. | Lisa Fearn | Discuss with colleagues across group around Thirteen approach to offering affordability checks to all customers at any stage of lettings process, but pro-actively at offer visit / pre-offer stage. | 2014-08-01 | 2015-02-01
Kay | MR2 | PT | A better pre-tenancy assessment is needed. All customers who are offered accommodation for their first rented social home should complete a 2 days course explaining how much it costs to manage a tenancy and how to sustain their tenancy. This might also be targeted at customers who are vulnerable and moving home. | Would agree that further consideration of pre-tenancy assessment/training is required. However, in the current environment, with difficulty letting homes, adding an additional pre-tenancy step would significantly impact on our ability to let homes. Enforcing a 2 day course would be difficult (and not suitable for all e.g.. people in employment or those who are confident with money) but could be used as a way of providing a reference for customers who are struggling to receive a reference as part of the vettings process. The course could also be provided to existing customers? Customers learn in different ways and 121 support during the first few weeks of tenancy maybe more beneficial? | Lisa Fearn | Discuss with colleagues across group around Thirteen approach and in consultation with customers around a proposed pre-tenancy/ new tenancy course or alternatively we are proposing to introduce joint/multi sign ups sessions which would include financial assessment. Also to discuss 121 support during first 12 months of tenancy. | 2014-08-01 | 2015-02-01
Chris | MR3 | WP | The Welcome packs should be more professional, simplified and some of the papers should be given at offer or viewing stage to ensure customers have a better understanding and information about their tenancy. New tenants should be asked to sign a checklist that they have been given and understood the contents | Agree that paperwork needs to be professional, simplified and consistent. There is a working group looking at the Welcome sign up pack. This will be streamlined to focus on the importance of the contractual agreement. The neighbourhood teams will take the rest of the information to the welcome visit. | Julie McNaughton | Discuss with colleagues across group and customers around Thirteen approach to the sign up process ensuring also that neighbourhood teams visit in the property within first week or two? | Discussion and agreed approach by July 2014
Kay | MR4 | NT | A 6 weeks and 6 month visit should take place to enable the patch manager to check that the new customer is coping in their new home, reminding them of the contact details of the patch manager. This to be provided across Group | The timescales require reviewing and 6 weeks check may not be soon enough and additional checks would be beneficial in excess of the two indicated in order to build customer relationships and ensure new tenancies are success.JCs note - report suggests a visit within 2 days as well as 6 week and 6 month visits. This will be bespoke and may be sooner for some especially where it was identified that the tenants may have support needs or vulnerabilities. | Neighbourhood Managers across Thirteen | NMs to agree a timetable of visits/purpose of visits etc. |  | 2014-10-01
Kay | MR5 | F | Investigate access to recycled furniture or low cost furniture for new and existing customers | Need to explore whether recycled furniture is desired by customers. Need to promote alternative options better i.e. freecycle, Frade etc. | Lisa Fearn | Promote options further and also explore need around recycled items | Discussion and agreed approach by July 2014 | 2014-10-01
Kay | MR6 | C | All contact with customers to include a review and updating of customer profiling information held. | TH and HH have sent out a full survey to customers to update their profile. Contact team should check telephone and profiling information during contacts. Once IPACs and mobile working in place, this will be more possible via neighbourhoods teams. Unlikely to be all staff at all contact but agree it is a priority. | Adele McLaren | To review scripts to ensure that this is checked as part of telephone contacts | Discussed and agreed approach June 14 | Implement by end of July 2014
Kay | MR7 | C | A card to be sent on the anniversary of every tenancy to gather opinions around tenancy issues and support to stay in their home ( with a prize draw) | This could be costly and may yield a low return around surveys. Explore alternative approaches and how much it would cost to administer. Would be resource intensive if not automatically generated. Following the implementation of the new ICT system - this will be automated | Neighbourhood Managers across Thirteen | Carry out evaluation of this initiative | Discussion and agreed approach by July 2014 | New ICT system will be in place Summer 2015
Kay | MR8 | C | Both landlords to offer a 2-3 year customer contact visit where their tenancy is discussed. This will enable every customer feel valued, build trust and enable any signs of vulnerability or tenancy failure to emerge. | This would be resource intensive and all options of "checking in" with customers could be explored rather than a traditional style visit? Risk based visit approach re-directing resources where most needed maybe more pro-active and cost effective option. | Neighbourhood Managers across Thirteen | Carry out evaluation of this initiative | Discussion and agreed approach by July 2014
Stewart | MR9 | N | All local neighbourhoods should have access to local funding such as the ROAP funding at TH, to enable customers in community groups to improve their area and make the neighbourhoods a better place to live | This is something that would be discussed as part of the Customer involvement framework review. ROAP TH funding is in place as part of the "offer document" at transfer. | Stewart Tagg | Review via Customer involvement framework approach | Discussion and agreed approach by September 2014 | 2014-12-01
Stewart | MR10 | ST | Thirteen to explore some of the ideas in tenant reward schemes nationally which might enable greater tenancy sustainment | Would be useful to discuss this with customers/research and insight to be gained to enable further discussion | Paul Noddings | Review approach following insight and business case established to enable evaluation of this option. | Discussion and agreed approach by September 2014 | 2015-03-01
Kay | MR11 | MEXT | Customers who apply for an exchange or a transfer should do so through the Patch Manager who can discuss what might enable the customer to stay. Immediate visits should be carried out to see if the landlords can take action before they terminate their tenancy | Agreed that these visits will take place by neighbourhood teams although timescales around visits will need to be agreed. This will form part of the inspection visit to all tenants following a transfer application form or mutual exchange application being registered. This is to prevent losing tenants who may also leave the company through other landlords. | Neighbourhood Managers across Thirteen | NM/s to agree an approach to support customers who identify that they want to transfer/mutual exchange/terminate their tenancy | Discussion and agreed approach by July 2014 | 2014-08-01
Kay | MR12 | MEXT | Customers who need to move should be able to get support from a specialist person who can explore 2 and 3-way mutual exchanges and enable the move to release at least one of the customers from bedroom tax costs | This role would fit within the neighbourhood service. We would always want to pro-actively support and facilitate mutual exchanges as a low cost solution to meet customers rehousing needs | Neighbourhood managers | DF with colleagues to establish an approach in a thirteen context. | Discussion and agreed approach by July 2014 | 2014-10-01
Chris | MR13 | WR | The rules for allocations to change to allow those who can upsize and pay for this, to be able to do this. Staff should be trained to understand that the allocations policy allows those who can pay for 3 bed homes to upsize, even if they are under-occupying. | Allocations are via CBL sub regional scheme and customers do have some flexibility to upsize i.e. 1/2 bedroom need for individuals and couples; 2/3 for couple/single with one child etc. although priority goes to customers who have a need for the number of rooms indicated. These discussions do take place with customers. Discussion required around enabling single people to apply for properties much bigger than their needs on an area basis in particular where there is low demand but customers can afford to upsize. | Julie McNaughton | Establish a unified approach in a Thirteen context. We will advertise based on need and if cannot allocate then can offer to others. Needs implementation of the new officers and teams from September to ensure this message goes across all teams | August 2014. | September 2014 - all teams will be togather and be in the same message
Chris | MR14 | T | A customer who says they are leaving should be visited not just for repairs when the tenancy has ended, but immediately as notice is given by the patch manager to see if it is possible to support them to remain in their home. | Agreed. EH & TVH voids Task & Finish Group have agreed a new process i.e. the pre-termination inspection is carried out by the neighbourhood teams instead of the empty property team, as they have the local knowledge in terms of tenancy conduct and any issues that need to be addressed. The pilot is working well and it is anticipated that it will be rolled out Group wide in the next few weeks/months. Links to Support to Stay initiative and Neighbourhood Sustainability Pilots. Patch manager must now speak to everyone who is going to see if they can persuade them to stay | Neighbourhood Managers across Thirteen & Julie McNaughton | Discuss agreed approach | 2014-07-01 | 2014-11-01
Chris | MR15 | V | The minimum void standard should be increased to to compete with the private rented sector and give customers the best possible start in their new home. The homes should always be deep cleaned, so customers can move in with the minimum of effort. When in future the void standard is reviewed, it should incorporate decoration issues and customers to be involved in this review | On-going discussions are in place around minimum standard and our approach to empty property management. Further work is now required in a group wide context. The standard maybe linked to size/location to determine the standard. | Julia Kett | Project team approach required to agree new approach to managing voids in a thirteen context | 2014-07-01 | Board will agree the strategy by December 2014 with March 2015 implementation
Chris | MR16 | I | Investment works not to be brought forward in a property when a customer leaves as this causes upset on the estate, when the former customer may have moved out due to delays in getting the work done | Links to the Empty homes strategy and void working party, need flexibility and consideration of the local circumstances. Need to work out what the patch officer can do to enable people to stay and how we ensure clear consistent message is communicated to the wider customer base of our approach | Mark Robson/Nik Turner | Agree approach, links to Geoff Prior's work on 3 voids standards and the timescales for this above. |  | December 2014 Board - agree the Strategy. March 2015 implementation
Mike | MR17 | I | Customers to be involved in the investment programme priorities and for landlords to be less reliant on the database | Customer consultation as part of a task and finish group when AMS strategy is approved | Geoff Prior/Nik Turner | Task and finish group in place | 2014-11-01 | 2014-12-01
Chris | MR18 | F | TH and HH to have a comprehensive solution to access furniture/white goods for new and existing customers. A conversation should be had with the customer when the home is viewed to enable the new customer to pay more on the rent for white goods, carpets, decoration or whatever a customer needs | On-going discussions are in place around minimum standard and our approach to empty property management. Further work is now required in a group wide context. A charge on the rent is not possible as Thirteen are unable to offer loans currently and would always look at partners i.e. credit unions who have this facility to support these types of requests around white goods/carpets etc. Financial inclusion and empty property teams will share information so that the customer is given the relevant information on viewing. This action links in with access to furniture for existing customers. | Julia Kett/Lisa Fearn | Further discussion required as part of service review on empty properties. Lisa to work through incentives like Smartbuys. Kay to develop the model with Lisa. Chris to work through with patch officers what under menu 3 of the void standard are the incentives that can be offered to applicants | Project outcomes to be agreed by August 2014 | December 2014 Board - agree the Strategy. March 2015 implementation | JK and LF met 30.5.14. The financial inclusion team will share info on credit unions and the empty property teams on second-hand furniture provision. JK will update LF on outcome of service review on empty properties. Funding will need to be identified to facilitate these type of loans for credit union members.
Kay | MR18 | F | A conversation should be had with the customer when the home is viewed to enable the new customer to access a small loan to own the goods/services that they need, paid back as an extra charge on their rent until the loan is paid off | Agree that this is a priority. Currently TH has a £50K loan scheme for new and existing customers to access low cost furniture via low cost loans. Further promotion is required. Hartlepool also have a scheme available which HH customers can access. Financial inclusion and empty property teams will share information so that the customer is given the relevant information on viewing. Project plan to clarify access to Moneywise, Tandem and Tees Credit union | Julia Kett/Lisa Fearn | Further discussion required as part of service review on empty properties | Project outcomes to be agreed by August 2014 | 2014-10-01 | JK and LF met 30.5.14. The financial inclusion team will share info on credit unions and the empty property teams on second-hand furniture provision. JK will update LF on outcome of service review on empty properties. Funding will need to be identified to facilitate these type of loans for credit union members.
Stewart | MR19 | ST | A number of new strategies for inclusion, tenancy support, affordable warmth and income management did not have accompanying action plans. They were not promoted across both landlords. Customers would like to be involved in shaping of those action plans and monitoring the delivery of new services | All strategic documents in a group context will have an action plan, follow a consistent approach and will be monitored and reviewed via business development team. | Eric Summers/Stewart Tagg | Discussion to take place around the role that customers can play in the review of strategic action plans. | Approach agreed corporately | 2014-06-01
Kay | MR20 | WR | Landlords to be clear on council and landlord access to DHP and ensure access has been achieved to both of these. All customers receiving DHP should have the end date/renewal date and be informed as soon as possible of any extension to DHP. This information should be included on the “rent account” viewing area of the websites | Clearer approach to be reviewed via Tandem team. Agree re adding information to rent account viewing areas of the website although no promotion of LDHF on website as Board decision not to promote widely to avoid raising expectations. Targeted approach preferred. | Lisa Fearn / Rob Thompson | Information included in the rent account viewing area of the website as well as generall yin other areas of the website | 2014-07-01 | 2014-12-01
Kay | MR21 | WR | Boards to review their decision to allow landlord DHP to those who have a shortfall of less than 10% and be clear why the arrangement in Prior and Melsonby and Port Clarence is not available for all customers | The LDHF will be reviewed by Board during 2014/15 and was thoroughly reviewed in February 2014 by Board where there was clear understanding based on business decisions around why certain customers in less sustainable areas were given support and other areas did not. LDHF will be reviewed by all Boards across Thirteen during 2014/15 | Kay Glew | Board discussion and officer discussions to take place in order to agree Thirteen's approach to welfare reform | 2014-07-01 | 2014-11-01
Kay | MR22 | MA | Financial advice should be promoted for all customers and not just to those in arrears. Customers may be paying their rent and getting into debt with other bills | Agreed and is promoted to all customers - i.e. website, telephone messages, face to face discussions etc. Credits on accounts to be regularly reviewed to ensure that any credits can be utilised to pay off other debts. | Lisa Fearn/Rob Thompson | To agree further promotion opportunities/group wide approach to managing credits on account (raised in main body of the report) | Discuss and agree approach by July 2014 | 2014-10-01
Kay | MR23 | ST | An early morning and evening appointment system (like WVAC) to be implemented across all services and all landlords and performance managed to show how well each of the landlords are performing | Appointments are available to meet customers needs and adapted based on customers circumstances. No recognised need currently established and contact team is very quiet 8- 9 and 6-8p.m. Further review is required. | Adele McLaren | Promote on the website access to Tandem including out of hours appointments | Promotion - July 2014 | 2014-10-01
Kay | MR24 | DI | Posters and adverts to let everyone know that the landlords can help you “get on line” and help you with employment. These should be displayed in as many places as possible, for example: Tristar TV, community centres, libraries, communal areas in flats, GP surgeries and shops | Agreed | Lisa Fearn | To agree publicity approach |  | 2014-08-01
Kay | MR25 | DI | The videos made to give information on tenancy sustainment should be linked from the landlord home page and more information on your own tenancy should be accessed from the website. | Agreed | Lisa Fearn/NMs | To agree approach to implementation |  | 2014-08-01
Kay | MR26 | DI | The user-ability of the website needs to be bigger and bolder and important messages for customers should be agreed with customers. In particular, the tenancy sustainment offer and information on the Bromford and Cestria websites are a good benchmark. | Agreed | Lisa Fearn/NMs | To agree approach to implementation | Updated by August 2014
Kay | MR27 | WR | Specific section on each landlord’s website called “Welfare reform” which gives up-to-date, comprehensive and consistent advice to customers, including what help is offered to move and the advice that is available. This should be placed on the home page. | Agreed | Lisa Fearn/Rob Thompson | To agree approach to implementation | Updated by August 2014 | 2014-10-01
Mike | MR28 | I | Customers should be informed when investment and improvement works are to be undertaken in order to prevent people terminating their tenancies prematurely | We have a 5 year plan and intend to publish a 2-3 year plan for customers following the approval of the Asset Managament Strategy in Dec 14 and Fuel Poverty strategy in Sept 14. | Geoff Prior | Consider as part of Asset Managament Strategy and Fuel Poverty strategy |  | 2014-12-01
Mike | MR29 | E | The new energy consortia OVO should offer their reduced costs energy to valuable existing customers as well as new customers |  | Mike Kay | Subject to business case being approved by the thirteen board.
Stewart | MR30 | ST | Rent Policy allows the landlords to charge above or below the recommended rent for that home. Flexibility to be considered where storage heaters are fitted and where rents in our homes are higher than the local rents in the private sector | Not appropriuate to use the + or- 5% tolerances, need to priorotise the replacement heating systems | Stewart Tagg |  | Agreed not to deliver | Undeliverable
Kay | MR31 | E | All landlords across Group to set up a fund for the customers to change over form key meters | Funds to be considered as part of hardship and credit union developments | Lisa Fearn | Discussion with customers required around establishing need for services | Updated by Oct 14 | 2014-12-01
Mike | MR32 | E | All landlords across the Group to have a strategy for promoting energy switching and door-step advice to make best use of energy in every customers home | This is part of the ESCO project and will be considered by Boards in Sept 14. Recruit, train and develop "Community Energy Champions" to take forward Energy advice in their communities | Mike Kay | Subject to business case being approved by the thirteen board. | 2014-09-01 | 2014-12-01
Kay | MR33 | E | TH customers should be informed how they can opt out of the water contract | This is available and has been undertaken by several customers although not widely published. Agree that customers could be informed of how this is possible in conjunction with NWB and this to be delivered thorugh a poster campaign in conjunction with advice on how to switch from key meters | Adele McLaren | Discussion with NWB and agreed approach to removal of this element of charge as per previous cases. We appreciate that a number of customers are considering warer meters to help monitor and control consumption/ charges . |  | 2014-08-01
Chris | MR34 | WR | VIPs to undertake an investigation into the offer made in the private sector and a separate investigation into those subject to the bedroom tax to be able to talk to them about the support they need. | Julie to work with Jonathan Cannon from CI team on a CSI project to her brief starting July 2014. | Julie McNaughton | CSI project for HH and TH to investigate PRS offer in July/August 2014 | August 2014. | 2014-12-01 | Mystery shopping to be carreid out in July on the Private Rented sector offer by CSI group
Kay | MR35 | E | Basic training on energy advice, support to stay, money and benefit advice to be given to all customer facing staff. | This would be resource intensive for all customer facing staff and better for trades to refer customers to the contact team to provide best possible advice. Training to be concentrated on neighbourhood teams. All front facing staff will also be aware of which department to refer into or to contact for advice. | Neighbourhood managers across thirteen | Agree training programme following recruitment into new roles. | Establish training needs for new neighbourhood teams | 2014-10-01

## abbrev
Abbreviations
C | Customer contact
DI | Digital Inclusion
E | Energy Advice
Em | Employability
F | Furniture
I | Investment works
MA | Money Advice
MEXT | MEX/Transfers
N | Neighbourhood
NT | New tenants
O | Older tenants
PT | Pre-tenancy
ST | Stratgeic
T | Terminations
V | Voids
WP | Welcome Pack
WR | Welfare Reform
MR | Main recommendations