Complaints and Customer Feedback Action Plan

| Recommendations from Scrutiny Assembly | Key Action(s) | Who Responsible | Timescale | Progress |
| --- | --- | --- | --- | --- |
| Management of the complaints system - BCH to sign up to Housemark Complaints Charter, demonstrating to customers that all complaints are welcomed, taken seriously, resolved and learned from. - Review staff guides, policies and procedures. Develop master document for staff. Develop a process map to demonstrate flow for improved understanding for users. - Review Orchard system and investigate the ability to link complaints and to log all initial enquiries at the first point of contact. Continue to expand Orchard to capture all contact and feedback including complaints, compliments and comments, individual actions such as emails, phone calls etc relating to all enquiries from customers. - Completion of evaluation forms and a system of monitoring outcomes. Feedback reporting process across services to implement actions. - Improve communication with customers and across services. Develop communication strategy. | Investigate costs, process and benefits. Identify other organisations that have this charter, gather feedback. Discuss information with SMT. Make recommendation to Access & Customer Care Group. Review current process and identify ways to improve. Incorporating any other actions within this action plan e.g. staff training. Produce an agreed process, liaise with service managers and other key members Implement changes Work with IT team to investigate the use of CRM and agree any timescales. Incorporate any actions for the development of the contact centre. Identification of training needs Review current evaluation forms identify issues. Review how lessons learned can be recorded and performance data captured within the system. Incorporate in to management and team meetings Review internal and external communication strategy. Raise staff awareness of process. Link across services and embed within practice. Report to Acc & CC group | Sara Acc & CC Group Sara/IT Service Managers Sara/Sharon P Service Managers IT Sara Sara/ IT SMT/Service Managers Maggie/Denise/Sara Sara/Service Managers Sara | May 2013 September 2013 (this may move following other actions within the plan) March 2014 September 2013 June 2013 |  |
| Performance Monitoring - Review current performance monitoring and reporting process. Enhance Orchard system to enable performance data to be produced. Develop process for discussing performance across teams. Develop learning from analysis of performance. | Agree performance reporting requirements for service managers. Develop reporting process Include performance reporting within communication process Identify training needs of SIP’s members so they can understand and challenge service performance Agree higher level reporting with Access and Customer Care Group | Sara/IT/Service Managers Sara/CI Team Sara | September 2013 |  |
| Front Line Services - All staff to be trained to use the system correctly. Enable staff to respond to customer complaints and provide good customer care. - Review all avenues for the collection of customer feedback is filtered in to the system, inclusive of Cllr enquiries. Review the current ability for customers to “fast tracking” complaints via the councillor. - Review customer feedback process ensuring that all feedback is captured at first point of contact and recorded within the system. - Review reception facilities at Coastal House to enable staff to respond to customer enquiries appropriately. - Review current provision of IT within the reception area. Enhance privacy for customers when using these facilities. Ensure provision is accessible for customers with mobility issues - Review current complaints process to enable clear understanding and communication to both staff and customers. Communicate with customers appropriately. Ensure customers are provided with reference numbers for stage 1 complaints. Provide all customers with the opportunity to complete satisfaction surveys allowing them to escalate complaints via these surveys if they wish to do so. Improve recording, reporting and monitoring of stage 1 complaints - Review current administration process for customer feedback across all teams. Ensure all teams manage complaints appropriately - Develop reporting processes across BCH, using the appropriate strategic leads/groups to deliver and monitor progress. Identify system improvements to ensure management and reporting of customer feedback are in place. - Review current service provision of the free phone number and resources to deliver customer services. Communicate with customers different methods of communicating with BCH. - Investigate the use of technology to enable staff to deliver services effectively when off site i.e. how staff can log repairs - An out of hours and out of office procedure and policy should be developed for capturing all feedback. | Refresh staff training on customer feedback. Embed customer care across all services Identify all sources of collection for customer feedback. Assess process of recording and responding. Make recommendations for recording within Orchard. Continue awareness raising with Cllr’s regarding complaints raised outside of the customer feedback process. Develop Orchard to enable recording of all customer feedback. Develop performance reporting process. Customer care training Health & Safety Training- de-escalation Review current risk assessment for reception Identify availability of current IT facilities for all customers. Investigate ability to install 2nd free phone Identify costs and make recommendations to Acc & CC group Review current communication strategy, agree how BCH are to communicate with customers and internally. Review policy, leaflets, user friendly, wording, understanding Incorporate into Orchard developments and staff training Record and report on stage 1complaints Identify current processes in teams. Discuss issues with managers, identify solutions and make recommendations to Acc & CC group Review communication strategy; identify links to delivery plan, relevant strategies and team plans. Review developed performance data within SMT and cascade actions to Acc & CC group Deliver action plan and report back to Acc & CC group on a bi-monthly basis and cascade appropriately. Standing agenda item on all team meetings. Develop single point of contact for customers using the hot line to deliver this service. Review IT provision and needs to develop this service. Review current performance processes does this provide adequate information or require development Identify staff training Communicate with customers appropriately and within agreed timescales Review impact of the office closures has this increased number of enquiries Develop lone working capabilities of housing services. Identify how the different IT packages can be linked to Orchard and enable effective working for all staff. Incorporate developments across BCH to ensure a joined up approach in developing this provision- e.g. welfare reform action plan Identify any funding issues/resources Review current out of hour’s provision from Vitaline. Agree a process for recording customer feedback. | Sara Service Managers Sara/ IT Sara/IT Paul/ H&S Sara/IT Sara/IT Service Managers IT/Service Managers IT/Service Managers Sharon P/IT Maggie/IT Denise | On going September 2013 September 2013 March 2013 August 2013 September 2013 (this may move following other actions within the plan) May 2013 May 2013 March 2014 March 2014 April 2014 | On going target, training previously completed following system update, new staff to be trained as required Risk Assessment reviewed, actions being implemented. Staff attended training |
| Customer Satisfaction - Review of the way the ALMO relationship is communicated to the customer should be made and a strategy developed to address this. - Develop methods for collecting satisfaction surveys from customers, such as e-mail, and telephone. Develop links of satisfaction surveys to complaints analysis. - Review current appointments policy including compensation process, identify if this can be cascaded across other services | Develop communication strategy for BCH which clarifies how it is different to the Council Deliver clear communication to customers using current methods- Viewpoint, website etc. Develop CRM, enabling BCH to have more up to date information on customers. Investigate how this system can be used to improve services, how the information can be utilised to direct service development in conjunction with other methods. Analysis Star Survey Develop smart methods of data collection. Link data collection across services to enable analysis and service improvements Review policy, identify if this can be adopted across services. Identify issues, costs and service implications. Carry out any relevant benchmark. Discuss with SIP, make recommendations to Acc & CC group | Maggie/Denise/Sara IT/Sharon P/Service Managers Ian F | June 2013 March 2014 October 2013 |  |
| Tenant Involvement - Review management and operation of the complaints panel. Identify requirements of the panel following any changes in the current customer feedback procedure. Consider whether membership of the complaints panel should be anonymous and protected in the same way as mystery shoppers. Review risks associated with panel membership being public information as part of the customer feedback process | Review role of the panel, identify areas for improvement. Identify any training requirements of panel members. Consult with panel members. Assess risk to tenants- make recommendations to group Complete a risk assessment on panel members identify as part of the current process. Put controls in place to minimise risks. | Sara Sara | June 2013 June 2013 |  |
| Customer Information, Documents and Policies – Customer Charter - Review the customer charter to expand the offer for feedback (and complaints) beyond the minimum and what is expected and ensure it matches and links with the procedure designed to meet it. Customer Feedback Procedure - Rewrite the staff procedure taking on board the changes and recommendations to the process. Develop a master document to which all other documents in the suite are linked and schedule for regular review. Customer Feedback and Complaints Leaflet - BCH to work with customers to rewrite the leaflet in a more simple, clear and customer friendly way. Ensure communication regarding complaints is clear, encouraging customer to provide feedback in order to deliver service improvements. Habitual and Vexatious Complaint Policy - Review the staff procedure inclusive of any changes and recommendations to the process. Link to the master feedback procedure. Ensure that the procedure is scheduled for a regular review. Compensation Payments BCH information Series - Work with customers to rewrite the leaflet in a more simple, clear and customer friendly way. Linking it with all other leaflets in the series and scheduling a regular review of it. Website - Review website and the way information is communicated to customers. The layout and design of the website should be overhauled in line with other organisations. The content should be reviewed to be clearer and use plain English and more customer friendly language, with the use of pictures, diagrams and charts increased | Work with scrutiny group and identify solutions Carry out benchmarking across other providers. Make recommendations Feedback to appropriate individuals and Acc & CC group As above Recommendations to be included in communications strategy, to include internal recording methods. Identify document control process As above Identify and agree BCH website development. Review current information from customers such as star survey, customer information on orchard, other survey results Identify what council is doing re website, link to communication strategy. Ensure all leaflet are linked to others in the series and is scheduled for regular review. As above. Develop a clear procedure and staff guidance, definitions. Communicate to staff. Develop a process for managing these complaints and recording information on the system which can be accessed by all departments. As above Develop a clear procedure and staff guidance, definitions. Communicate to staff. Develop a process for managing these complaints and recording information on the system which can be accessed by all departments. As above Identify and agree BCH website development. Review current information from customers such as star survey, customer information on orchard, other survey results Identify what council is doing re website, link to communication strategy. Ensure all leaflet are linked to others in the series and is scheduled for regular review Identify costs and budget | Sara/CI Team Scrutiny Panel Sara/IT Scrutiny Panel Sara/CI Team Scrutiny Panel Sara/CI Team Scrutiny Panel Ian F Scrutiny Panel Sara/CI Team/IT Scrutiny Panel | October 2013 October 2013 October 2013 October 2013 October 2013 March 2014 |  |
| Training - Develop staff training in general customer service and dealing with feedback and complaints. Identify additional training requirements for staff teams that are more customer facing and deliver training that meets their needs. Identify how other organisations have embedded a “customer” culture and what good practice they can offer. | Liaises with managers and HR, identify needs of service teams. Develop a process of identifying refresher training. Link performance data to teams to assist in service development including training requirements. Standing item in team meetings and IPA’s Carry out benchmarking across other providers, identify organisations that have made cultural changes and how these have been implemented. | Service Managers/HR | March 2014 | In process of identifying staff training requirements as part of the IPA process. Ongoing action through out the year. |