| Repairs Scrutiny |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | Group or Individual | Support or Resources Required | Facilitated By | How much time is required to complete the task? | Training Requirements (Supported By) | Date Arranged |
| Tasks |  |  |  |  |  |  |
| Team Set up | GROUP | IDENTIFY STRENGTHS / WEAKNESSES / SKILLS / INTRODUCTIONS / GROUND RULES / ROLES IN GROUP / JARGON DICTIONARY / CALENDAR TIMESCALES | INVOLVEMENT TEAM | 4 HOURS |  | 11/06/2015 |
| Defining Customer - Who is the customer for repairs? | GROUP | FACILITATED BY MEMBER OF STAFF | INTERVENTION TEAM | ½ DAY DONE IN 1 DAY |  | 17/06/2015 Room 211 2nd Floor 10.00-15.00 |
| Defining Purpose - What do customers need from us? | GROUP | FACILITATED BY MEMBER OF STAFF | INTERVENTION TEAM | ½ DAY |  |  |
| Meet with Service Leads for Repairs | GROUP | FACILITATED BY MEMBER OF STAFF | INVOLVEMENT TEAM | 1 HOUR 15.00-16.00 |  | 17/06/2015 Room 211 2nd Floor |
| Understanding demand - What is Value and Failure demand? | GROUP | FACILITATED BY MEMBER OF STAFF (CREATE STANDARD DATA CAPTURE SHEET FOR CI’s) | INTERVENTION TEAM | DAY 10.00-16.00 |  | 01/07/2015 Thackley Room |
| Listen and capture demand in the service | INDIVIDUAL | HEADSETS / NOTEPAD / NOTEPADS / SHEETS / FLOORWALKER | INVOLVEMENT TEAM | 1 WEEK CAPTURE Meeting 13/07/15 12-4 Heaton 2 for Data 2ND WEEK BOOKED PROVISIONALLY | HOW TO SET UP HEADSETS (Involvement Team) | 6th to 17th July 2015 |
| Designing Demand Capture Sheet and decide who needs to complete these? | SMALL GROUP – AGREED BY MAJORITY THEN CIRCULATED TO ALL MEMBERS | STAFF MEMBER / LAPTOP / PREVIOUS SHEETS FOT TEMPLATE / AGREE TIMESCALE LEFT IN DEPARTMENTS | INVOLVEMENT TEAM | 2 HOURS 10.00-12.00 |  | 20/07/2015 Bierley Room |
| Deliver Demand Capture Sheet to front line services EDIP | SMALL GROUP / INDIVIDUALS | PHOTOCOPIER / TRANSPORT / STAFF | INVOLVEMENT TEAM | 10am Onwards |  | 21/07/2015 Heaton 2 |
| Demand Analysis - what is it telling us? | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM | INVOLVEMENT TEAM | 10.00 – 16.00 |  | 04/08/2015 Heaton 2 |
| Introducing Flow | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM | INTERVENTION TEAM | 10.00 – 16.00 |  | 11/08/2015 Thackley Room |
| Introducing Measures | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM | INTERVENTION TEAM | 10.00 – 16.00 |  | 18/08/2015 Heaton 2 |
| Introducing System Conditions | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM | INTERVENTION TEAM | 10.00 – 16.00 |  | 19/08/2015 Heaton 2 |
| Out in the service mapping flow | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM | INVOLVEMENT TEAM | DAY | 2nd week of capture and demand will incorporate mapping the flow (Inspectors Choice) | N/A |
| Validate flow and gather measures | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM / CURRENT MEASURES | INVOLVEMENT TEAM | 13.00 – 15.00 | 1 week up to 01/09/15 for service heads to provide relevant measures required | 25/08/2015 Heaton 2 |
| Collate all findings | GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM | INTERVENTION TEAM | 10.00 – 16.00 |  | 03/09/2015 Heaton 2 |
| Meet Service Heads | SMALL GROUP | STAFF / NOTEPADS | INVOLVEMENT TEAM | 10.00 -12.00 |  | 04/09/2015 Thackley Room |
| Write Report | SMALL AGREED GROUP FOLLOWED UP BY ALL GROUP | STAFF / FLIP CHARTS / PENS / POST ITS / BLU TAC / BIG ROOM / LAPTOP | INVOLVEMENT TEAM | DAY | REPORT WRITING / EXCEL (Numbers taken in process of arranging training) | 07/09/2015 to 18/09/2015 |
| Present findings and report | 2-3 TO PRESENT TO EACH GROUP | DATES / TIMES / TRANSPORT | INVOLVEMENT TEAM | 4-6 WEEKS STAGGERED ACROSS WHEN GROUPS / BOARDS MEET | PRESENTATION SKILLS / POWERPOINT (Numbers taken in process of arranging training) |  |

(This is subject to change in case of unavoidable events or circumstances which mean parts cannot be completed at the given time. Any changes will be agreed by the Customer Inspectors, anyone affected by changes will be notified and the earliest possible time)